## IRA UTILIZATION 4TH QTR 2022
20% COMPONENT OF THE IRA UTILIZATION
FOR THE FOURTH QUARTER CY 2022
CURRENT LEGISLATIVE APPROPRIATION
FUNCTION/PROGRAM PROJECT ACTIVITY |  |  | LOCATION/ COVERAGE | TOTAL COST | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | NO. OF EXTENSIONS, IF ANY | REMARKS
[19 empty] | % OF COMPLETION | TOTAL COST INCURRED
SOCIAL DEVELOPMENT
| Recovery Assistance to Hog Raisers affected to African Swine Fever (ASF) |  | All Barangays | 10000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Support to COVID-19 related PPAs |  | All Barangays | 20000000 | [13 empty] | Jan.-Dec. 2022 | 4.511% | 902165
| Sub-total |  |  | 30000000 | [15 empty] | 902165
ECONOMIC DEVELOPMENT
| Concreting of Farm-to-Market Road |  | Various Barangays | 40261034.8 | [13 empty] | Jan.-Dec. 2022 | 0% | 0 |  | Under Procurement
| Road Widening |  | Various Barangays | 500000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Additional Funding for the Construction of Sumader SWIP |  | Brgy. Sumader | 20000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Rehabilitation of Spillway |  | Various Barangays | 2000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Concreting of irrigation Canal |  | Various Barangays | 5000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Rehabilitation /Excavation of Small Farm Reservior (SFR) |  | Various Barangays | 2000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Construction and rehabilitation of Diversion Dam |  | Various Barangays | 5000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Development of Public Market | [16 empty] | Jan.-Dec. 2022 |  | 0
| Installation of Cargo Lift (3 units) |  | Public Market | 5000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Installation of Elecrical Wirings for Bldg. 1-6 |  | Public Market | 3000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Sub-total |  |  | 82761034.8 | [15 empty] | 0
ENVIRONMENTAL MANAGEMENT
Solid Waste management Program
| Upkeeping & preservation of the City Waste Disposal Site |  | City Dumpsite | 500000 | [13 empty] | Jan.-Dec. 2022 | 95.85% | 479240.66
| Construction of Slope Protection & Drainage System along the Garbage pond & Concreting of Road Network |  | Various Barangays | 8000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Purchase of Dumptruck |  | n/a | 5000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Construction of Roadway Slope Protection |  | Various Barangays | 20000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Dredging of Waterways (rivers/ creeks/ canals) |  | Various Barangays | 2000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Sub-total |  |  | 35500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1.35% | 479240.66
| TOTAL SPA-20% DF |  |  | 148261034.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 6.284e-09% | 0.9317%
Supplemental Budget No. 3-Reversion- (20% Development Fund-CY 2015-2021)
SOCIAL DEVELOPMENT
| Construction of Covered Court at Barangay Quiom |  | Various Barangays | 4000000 | [13 empty] | Dec. 2022 | 0% | 0
| Sub-Total |  |  | 4000000
ECONOMIC DEVELOPMENT
| Purchase of Fertilizer for Distribution to Farmers |  | Various Barangays | 10000000 | [13 empty] | Dec. 2022 | 99.85% | 9985115
| Purchase of 4 Units Backhoe |  | n/a | 16000000 | [13 empty] | Dec. 2022 | 0% | 0 |  | Under Procurement
| Sub-total |  |  | 26000000 | [14 empty] | 38.4% | 9985115
| TOTAL SPA-20% DF |  |  | 30000000 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 33.28% | 9985115
GRAND TOTAL |  |  |  | 178261034.8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 6.376% | 11366520.66
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
|  | WILMA T. ICUSPIT | [16 empty] | ENGR. ALBERT D. CHUA
|  | City Budget Officer | [16 empty] | City Mayor