## IRA UTILIZATION 4TH QTR 2022
20% COMPONENT OF THE IRA UTILIZATION
FOR THE FOURTH QUARTER CY 2022
CURRENT LEGISLATIVE APPROPRIATION
FUNCTION/PROGRAM PROJECT ACTIVITY |  |  | LOCATION/ COVERAGE | TOTAL COST | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | NO. OF EXTENSIONS, IF ANY | REMARKS
[19 empty] | % OF COMPLETION | TOTAL COST INCURRED
SOCIAL DEVELOPMENT
| Recovery Assistance to Hog Raisers affected to African Swine Fever (ASF) |  | All Barangays | 10000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Support to COVID-19 related PPAs |  | All Barangays | 20000000 | [13 empty] | Jan.-Dec. 2022 | 4.511% | 902165
| Sub-total |  |  | 30000000 | [15 empty] | 902165
ECONOMIC DEVELOPMENT
| Concreting of Farm-to-Market Road |  | Various Barangays | 40261034.8 | [13 empty] | Jan.-Dec. 2022 | 0% | 0 |  | Under Procurement
| Road Widening |  | Various Barangays | 500000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Additional Funding for the Construction of Sumader SWIP |  | Brgy. Sumader | 20000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Rehabilitation of Spillway |  | Various Barangays | 2000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Concreting of irrigation Canal |  | Various Barangays | 5000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Rehabilitation /Excavation of Small Farm Reservior (SFR) |  | Various Barangays | 2000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Construction and rehabilitation of Diversion Dam |  | Various Barangays | 5000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Development of Public Market | [16 empty] | Jan.-Dec. 2022 |  | 0
| Installation of Cargo Lift (3 units) |  | Public Market | 5000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Installation of Elecrical Wirings for Bldg. 1-6 |  | Public Market | 3000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Sub-total |  |  | 82761034.8 | [15 empty] | 0
ENVIRONMENTAL MANAGEMENT
Solid Waste management Program
| Upkeeping & preservation of the City Waste Disposal Site |  | City Dumpsite | 500000 | [13 empty] | Jan.-Dec. 2022 | 95.85% | 479240.66
| Construction of Slope Protection & Drainage System along the Garbage pond & Concreting of Road Network |  | Various Barangays | 8000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Purchase of Dumptruck |  | n/a | 5000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Construction of Roadway Slope Protection |  | Various Barangays | 20000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Dredging of Waterways (rivers/ creeks/ canals) |  | Various Barangays | 2000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Sub-total |  |  | 35500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1.35% | 479240.66
| TOTAL SPA-20% DF |  |  | 148261034.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 6.284e-09% | 0.9317%
Supplemental Budget No. 3-Reversion- (20% Development Fund-CY 2015-2021)
SOCIAL DEVELOPMENT
| Construction of Covered Court at Barangay Quiom |  | Various Barangays | 4000000 | [13 empty] | Dec. 2022 | 0% | 0
| Sub-Total |  |  | 4000000
ECONOMIC DEVELOPMENT
| Purchase of Fertilizer for Distribution to Farmers |  | Various Barangays | 10000000 | [13 empty] | Dec. 2022 | 99.85% | 9985115
| Purchase of 4 Units Backhoe |  | n/a | 16000000 | [13 empty] | Dec. 2022 | 0% | 0 |  | Under Procurement
| Sub-total |  |  | 26000000 | [14 empty] | 38.4% | 9985115
| TOTAL SPA-20% DF |  |  | 30000000 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 33.28% | 9985115
GRAND TOTAL |  |  |  | 178261034.8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 6.376% | 11366520.66
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
|  | WILMA T. ICUSPIT | [16 empty] | ENGR. ALBERT D. CHUA
|  | City Budget Officer | [16 empty] | City Mayor

## TRUST FUND UTILIZATION 4TH QTR
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 4th QUARTER, CY 2022
Province, City or Municipality: BATAC CITY
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | Balance |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date |  | Previous Balance
Philhealth Capitation |  | 12906684.2 | 2011-2017 |  | 73.03% | 9426042.97 | 3480641.23 | 7649160.34 |  | ongoing | 3480641.23
Animal Bite Treatment Package |  | 1130000 | February 2017 |  | 99.5% | 1124557 | 5443 | 752657 |  | ongoing | 5443
TB-DOTS |  | 399975 | 2015-2017 |  | 68.48% | 273901 | 126074 | 273901 |  | ongoing | 126074
HCI Charges |  | 574675 | 2018-2019 |  | 0% | [5 empty] | 574675
Transfer for the Rehabilitation of Small Scale Irrigation Project | Brgy. Camandingan, Batac City, I.N. | 3000000 | June 13, 2014 delivery of materials |  | 100% | 2284116.5 |  | 2245966.5 |  | liquidated with refund of 715,883.50 Check # 638708 | 715883.5
Construction of Sumader SWIP | Brgy. Sumader, Batac City, I.N. | 29254500 |  |  | 63.09% | 29254500 | 0 |  |  | Second Billing paid under Voucher No. 100-2021-03-1161; Check No. 794803 | 0
Fund transfer for the conversion of existing Day Care Centers to Child Development Centers |  | 1000000 |  |  | 100% | 735206 | 264794 | 735206 |  | Fully liquidated, balance of P264,794.00 refunded under check no. 638775 | 264794
Technology Adoption & Commercialization of Hawaiian Ginger & Turmeric | Baligat, Camandingan, San Pedro | 2103093 | February 2017 |  | 100% | 1791754.88 | 853340.52 | 1782879.08 |  | Balance refunded under Voucher No. 100-2021-12-3856; Check No. 868222 | 311338.12
Rehabilitation of Baoa Diversion Dam | Baoa East, Baoa West | 1440000 | Receipt of Fund-July 2017 |  | 100% |  | 1440000 |  |  | with liquidating damages in the amount of P19,707.24 | 1440000
Establishment of Adolescent Friendly Health Facilities |  | 50000 | February 2018 |  | 100% | 50000 |  |  |  | liquidated | 0
Technology Adoption & Commercialization of Hawaiian Ginger & Turmeric | Baligat, Camandingan, San Pedro | 2103093 | Receipt of Fund December 2018 |  | 50% |  |  |  |  | Balance refunded under Voucher No. 100-2021-12-3856; Check No. 868222 | 2103093
Funding Support of Safe Closure and Rehabilitation Plan (SCRP) of Open and Controlled Dumpsite (Perimeter Fence) | Brgy. 31 Camandingan | 1822247.42 | Receipt of Fund December 2018 |  | 100% | 1822247.42 |  |  |  | First and Final Billing paid under Check No. 794602 in the amount of 1,822,247.42; with liquidation report | 0
Proposed Riverfront Promenade | Brgy. Ablan & Valdez | 7077100 | Receipt of Fund-March 2019 |  | 100% | 7042223.44 | 34876.56 |  |  | Liquidated: Final Billing paid under Voucher No. 100-2021-09-2728; Check No. 796089; Refund of 34,876.56 paid under Voucher No. 100-21-09-2806; Check No. 796091 | 34876.56
Riverfront Promenade Phase 2 | Brgy. Ablan & Valdez | 13750201 | Receipt of Fund-December 2019 |  | 82% | 4572740.74 |  |  |  | ongoing | 9177460.26
Performance Challenge Fund: |  | 3500000 | Receipt of Fund-December 2019 |  | 100% | 3490000 |  |  |  | Liquidated: First and Final Billing paid under Voucher No. 300-21-07-018; Check No. 688007; Refund of 10,000 paid under Voucher No. 300-2021-07-19; Check No. 688008 | 10000
Share of the City-2012 7171 Excise Tax- | [10 empty] | 0
Construction/Rehabilitation of Farm to Market Road | 22 rural barangays | 34500000 | October,2015 |  | 100% | 34167234.31 | 332765.69 | 34167234.31 |  | completed | 332765.69
Share of the City-Direct shares of Congressional Districts for the 2012 Excise Tax: | [10 empty] | 0
Farm to Market Road | rural barangays | 15000000 | November,2015 |  | 100% | 14280464.15 | 719535.85 | 14280464.15 |  | completed | 719535.85
Purchase of Various Equipment | 43 barangays | 40745187 | November,2015 |  | 92.15% | 37546995 | 12597192 | 37546995 |  | ongoing | 3198192
Buy -back and Other Marketing | [10 empty] | 0
Programs for Critical Alternative crops to tobacco |  | 4000000 | November,2015 |  | 89.55% | 3581998.24 | 418001.76 | 3581998.24 |  | ongoing | 418001.76
Local Government Support Fund: | [10 empty] | 0
SALINTUBIG(Sagana at Ligtas na Tubig sa Lahat) Provision of Portable Water Supply | [9 empty] | For Final Billing | 0
| Pimentel | 500000 | 2017-10-22 |  | 100% | [5 empty] | 500000
| Maipalig | 1060000 | 2017-10-22 |  | 100% | [5 empty] | 1060000
0
FY 2020 Local Government Support Fund-Assistance to Cities (Riverfront Promenade 3) |  | 10647492 | Receipt of Fund- November 2021 | [6 empty] | ongoing | 10647492
Local Government Support Fund- Financial Assistance to LGUs (Procurement of Rescue Kit) |  | 2500000 | Receipt of Fund -December 2022 | [7 empty] | 2500000
DSWD-RF01 | [10 empty] | 0
Cost for Viand and Rice for 1,050 Children in the implementation of SFP CY 2017 |  | 1890000 | Receipt of Fund-September 2018 |  | 50.21% | 948991.96 | 1890000 |  |  | Fully Liquidated, with a refund of 941,008.04; Check No. 638772 | 941008.04
Fund Transfer-Social Pension 3rd Qtr |  | 1264500 | Receipt of Fund-October 2018 |  | 100% | 1264500 | 0 | 1264500 |  | liquidated | 0
Fund Transfer-Social Pension 4th Qtr |  | 1264500 | Receipt of Fund-October 2018 |  | 100% | 1264500 | 0 | 1264500 |  | liquidated | 0
ATI-RTC I | [10 empty] | 0
Funding Support for the Sustainable Community Development Through the Conduct of Series of Training Under the Extension Program fro Agri-Fisheries and National Development (Expand) or Grant System |  | 905000 | Receipt of Fund-December 27, 2018 |  | 100% | 876294.28 | 28705.72 | 111357.38 |  | liquidated with refund of 28,705.71 Check # 638717 | 28705.72
DEPARTMENT OF ENERGY | [10 empty] | 0
ER 1-94 COVID related projects of the City Government of Batac (from the DOE) | City of Batac, Ilocos Norte | 200000 | August 2020 |  | 100% | 193836 |  |  |  | According to DOE, the balance of P6,164 will be used to purchase alcohol. | 6164
DANGEROUS DRUGS BOARD | [10 empty] | 0
Financial Assistance-Dangerous Drugs Board |  | 6000000 | Receipt of Fund- December 2021 | [6 empty] | Pre-Proc Conference on October 17, 2022 | 6000000
OFFICE OF THE PRESIDENT | [10 empty] | 0
Financial Assistance to cater and address the immediate needs of the people affected by the health crisis brought about by the Corona Virus Disease (COVID-19) per approved Memorandum dated March 4, 2021 | City of Batac, Ilocos Norte | 5000000 | Receipt of Fund March 2021 |  | 100% | 4963262 |  |  |  | Liquidated with refund to Office of the President amounting to P36,738.00 under Check No. 638811 | 36738
Financial assistance of people affected by Covid-19 | City of Batac, Ilocos Norte | 10000000 | July 2022 |  | 0% | 0 |  |  |  | Refunded to OP-Socio Civic Projects Fund under Check No. 638814
DEPARTMENT OF HEALTH-CENTER FOR HEALTH DEVT. I
One Covid-19 Allowance (OCA)- for the month of January 2022 |  | 732125 | Receipt of Fund- July 25, 2022 |  | 98.77% | 723125 |  |  |  | Liquidated; Balance of 9,000 refunded under Check No. 638818 dated August 17, 2022
One Covid-19 Allowance (OCA)- for the month of February 2022 |  | 799125 | Receipt of Fund- July 25, 2022 |  | 100% | 799125 |  |  |  | Liquidated
Meals, accomodation & transportation benegits as per Admin Order #2021-0062 for the period Sept 15 to Dec 19, 2020 |  | 210000 | Receipt of Fund- July 25, 2022 |  | 96.67% | 203000 |  |  |  | Liquidated. Balance of 7,000 refunded under Check No. 638818 dated August 17, 2022
One Covid Allowance for the month of April 2022 |  | 709625 |  |  | 75.16% | 533375 |  |  |  | One Covid Allowance for BHWs and some Job Orders in process. | 176250
One Covid Allowance for the month of June 2022 |  | 650625 |  |  | 82.48% | 536625 |  |  |  | One Covid Allowance for BHWs and some Job Orders in process. | 114000
Generics Awareness Month |  | 46600 | Receipt of Fund- October 2022 |  | 5.617% | 2617.4 |  |  |  |  | 43982.6
DSWD-RO I | [10 empty] | 0
Rehabilitation of Senior Citizen Building | [9 empty] | liquidating damages in the amount of P20,809.15 | 0
DEPARTMENT OF LABOR AND EMPLOYMENT RO1 | [10 empty] | 0
DOLE Regional Office 1 (Provision of various Processing Equpment for Peanut Processing (Self-Employed with insuficient income) |  | 758152 | Receipt of Fund- October 2022 |  | 0% | 0
Others: | [10 empty] | 0
C and G Environmental Management Corporation |  | 121000 | Receipt of Fund- September 2022
Commission on Population & Development (Social Protection for Adolescent Mothers and their Children) |  | 200000 | Receipt of Fund- September 2022 |  | 21% | 42000 |  |  |  |  | 158000
911 Library - The Delivery of Supplementary Reference and Research Materials through an Accessible Community Satellite Library for Modular Learning of the Learners of the Three Barangays (Bungon, Baay and Billoca) | Brgy. Bungon, Baay and Billoca | 270000 | Receipt of Fund-August 31, 2022 |  |  | 0 |  |  |  |  | 270000
PBSP-CHO PMDT |  | 7610 | December 2017 |  | 0% | 0 |  |  |  |  | 7610
Sustainable Development Goals-Family Based Actions for Children and their Environment in the Slims (SDG FACES) |  | 50000 | November 2017 |  | 0% | 0 |  |  |  | not implemented | 50000
Cash Donation Support to PNCR-Ilocos Norte Chapter |  | 3000 | March 2017 |  | 0% | 0 |  |  |  |  | 3000 | 9. Commission on Polpulation & Development (Social Protection for Adolescent Mothers and their Children)
Prizes for Most Outstanding Farmers |  | 100000 | January 2017 |  | 0% | 0 |  |  |  |  | 100000 | 8. C and G Environmental Management Corporation
Travelling Allowance for existing BNS for 2019 |  | 56400 | Receipt of Fund-June 2019 |  | 100% | 56400 |  |  |  | completed | 0
SOCIAL AMELIORATION PROGRAM | City of Batac, Ilocos Norte | 51700000 | April 2020 |  | 100% | 51700000 |  |  |  | Fully liquidated | 0
SOCIAL PENSION for Indigent Senior Citizen for the 1st Semester of 2020 | City of Batac, Ilocos Norte | 2319000 | June 2020 |  | 100% | 2319000 |  |  |  | Fully Liquidated, with a refund of 114,000; Check No. 638768 | 0
Provision of Water Pumps (Department of Labor and Employment) | City of Batac, Ilocos Norte | 1400000 | July 2020 |  | 100% | 1399950 |  |  |  | Voucher and check of refund in the amount of P50.00 was prepared under V#300-2021-03-009; check#638783 | 50
Travelling Allowance for existing BNS for 2022 |  | 55200 | Receipt of Fund-May 23, 2022 |  | 0% | 55200 |  |  |  |  | 0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
| FLORIDA S. CADANO |  |  |  |  | ENGR. ALBERT D. CHUA
| City Accountant |  |  |  |  | City Mayor

## UNLIQUIDATED CASH ADVANCES
FDP Form 12 - Unliquidated Cash Advances
UNLIQUIDATED CASH ADVANCES
As of DECEMBER 31, 2022
City of Batac, Ilocos Norte - General Fund
Name of Debtor | Amount |  |  |  | Amount Due
(In alphabetical order) | Balance |  | Date Granted | Purpose | Current |  |  | Past Due
[5 empty] | Less than 30 days | 31-90 days | 91-365 days | Over 1 year | Over 2 years | 3 years and above
NONE
TOTAL | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
We hereby certify that we have reveiwed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
FLORIDA S. CADANO | [5 empty] | ENGR. ALBERT D. CHUA
City Accountant | [5 empty] | City Mayor
0

## CASH FLOW 4TH QTR
FDP Form 9 - Statement of Cash Flow
(COA Form)
STATEMENT OF CASH FLOWS
For the Period Ended December 31, 2022
City of Batac, Ilocos Norte
ALL FUNDS
Cash Flows from Operating Activities:
Cash Inflows:
|  | Collection from Taxpayers |  | 64618702.39
|  | Share from Internal Revenue Collections |  | 741305374
|  | Other Share from National Taxes |  | 259283152.84
|  | Receipts from Sale of Goods or Services |  | 59155032.37
|  | Interest Income |  | 2535617.69
|  | Other Receipts |  | 95910067.18
|  | Total Cash Inflows |  | 1222807946.47
Cash Outflows:
Payments:
|  |  | Of Expenses | 326478583.63
|  |  | To Suppliers/Creditors | 164370360.41
|  |  | To Employees | 106311047.8
|  | Other Expenses |  | 159493214.91
|  | Total Cash Outflows |  | 756653206.75
| Net Cash from Operating Activities |  |  |  | 466154739.72
Cash Flows from Investing Activities
Cash Inflows:
|  | From Sale of Property, Plant and Equipment |  | 0
|  | From Sale of Dept Securities of Other Entities |  | 0
From Collection of Principal on Loans
|  |  | to Other Entities | 0
|  | Total Cash Inflows |  | 0
Cash Outflows:
|  | To Purchase Property, Plant & Equipment |  | 115867022.42
|  | To Purchase Debt Securities of Other Entities |  | 0
|  | To Grant/Make Loans to Other Entities |  | 0
|  | Total Cash Outflows |  | 115867022.42
| Net Cash from Investing Activities |  |  |  | -115867022.42
Cash Flows from Financing Activities
Cash Inflows:
|  | From Issuance of Debt Securities |  | 0
|  | From Acquisition of Loan |  | 0
|  | Total Cash Inflows |  | 0
Cash Outflows:
|  | Retirement/Redemption of Debt Securities |  | 0
|  | Payment of Loan Amortization |  | 0
|  | Total Cash Outflows |  | 0
| Net Cash from Financing Activities |  |  |  | 0
Net Increase in Cash |  |  |  |  | 350287717.3
Cash Beginning of the Period, January 1, 2022 |  |  |  |  | 1851886217
Cash at the End of the Period, December 31, 2022 |  |  |  |  | 2202173934.3
CERTIFIED CORRECT: |  |  |  | NOTED BY:
FLORIDA S. CADANO |  |  |  | ENGR. ALBERT D. CHUA
| City Accountant |  |  | City Mayor

## LDRRM FUND 4TH QTR
Republic of the Philippines
Province of Ilocos Norte
City Government of Batac
Report on Utilization of Disaster Risk Reduction and Management Fund | [6 empty] | january | february | march | april | may | june | july | august | september | october | november | december
As of December 31, 2022
Particulars | Quick Response Fund (QRF) 30% | Mitigation Fund (70%) | NDRRMF | From Other LGUs | From Other Sources | Total
A. Sources of Funds:
Currrent Appropriation | 12815451.88 | 29902721.05 |  |  |  | 42718172.93
Continuing Appropriation | [5 empty] | 35969476.1
2021 |  | 5406966
2020 |  | 7289525
2019 |  | 8553545
2018 |  | 2339826.94
2017 |  | 7614696.5
2016 |  | 4764916.66
Previous Year's Appropriations transferred to the Special Trust Fund | [5 empty] | 26702082.01
2019 |  | 11435457.97
2020 |  | 6683258.27
2021 |  | 8583365.77
Donations |  | 3000 |  |  |  | 3000 |  | -450000
Total Funds Available | 12815451.88 | 92577279.16 |  |  | 0 | 105392731.04
B. Utilization
Disaster Prevention and Mitigation
Clearing, pruning, brushing & cutting of trees in different barangays & schools |  | 419578.25 | [6 empty] | 43737.05 | 43543.15 | 15602.2 | 36431.2 | 93776.4 | 65211.1 | 21600.3 | 10078.4 | 25903.5 | 63694.95
[9 empty] | 21514.85 | 25692.7 | 4753.3 |  | 36470.4 | 40274.1 | 12300 | 10078.4 | 25903.5 | 16538.2 | 47
[9 empty] | 7888 | 17850.45 | 5156 |  | 18257.7 | 24937 | 9300.3 |  |  | 16543.1 | 933
[9 empty] | 7555 |  | 5692.9 |  | 39039.3 |  |  |  |  | 10782.4 | 1005
[9 empty] | 6779.2 |  |  |  | 9 |  |  |  |  | 19831.25 | 744
Cash for work program before calamities |  | 994500 | [11 empty] | 697000 | 258400 |  |  | 39100
[14 empty] | 32300 | 22100 |  |  | 39100 | 338
[14 empty] | 20400 | 18700
[14 empty] | 22100 | 22100
[14 empty] | 22100 | 22100
[14 empty] | 22100 | 20400
[14 empty] | 22100 | 20400
[14 empty] | 22100 | 22100
[14 empty] | 22100 | 5100
[14 empty] | 32300 | 20400
[14 empty] | 22100 | 30600
[14 empty] | 22100 | 32300
[14 empty] | 20400 | 22100
22100
22100
20400
22100
22100
27200
20400
22100
22100
22100
22100
22100
20400
22100
22100
22100
20400
18700
22100
Dredging, declogging, & cleaning of rivers, creeks, canals, small farm reservoirs & other waterways |  | 0
Disaster Preparedness
Conduct of capacity training of C/BDRRMC, SDRRMC, NGOs, Govt & private sectors & volunteers on DRRM |  | 478320 | [11 empty] | 9000 | 156520 | 28200 |  | 284600
[14 empty] | 3000 | 156520 | 28200 |  | 8500 | 861
[14 empty] | 3000 |  |  |  | 222600 | 1008
[14 empty] | 3000 |  |  |  | 42000 | 674
[18 empty] | 1000 | 168
[18 empty] | 1000 | 169
[18 empty] | 1000 | 170
[18 empty] | 1000 | 171
[18 empty] | 7500 | 172
Updating of various CDRRM plans |  | 0
Conduct of earthquake, flood & fire evacuation drills Oplan Ligtas Pamayanan |  | 0
Info Education Campaign; Early Warning Systems & Pre-evacuation Management, Disaster preparedness; production, |  | 28974.4 | [11 empty] | 22520 |  |  |  | 6454.4
[14 empty] | 22520 |  |  |  | 6454.4 | 1096
formulation & distribution of materials (manuals, leaflets, pamphlets, flyers, brochures, posters, early warning
signages); dialogues with the school & community; and others
Conduct of DRRM Related Contest |  | 0
Stockpiling & Prepositionig of Supplies & Materials (Food & Nonfood items/medicines) |  | 1363700 | [8 empty] | 971100 | [6 empty] | 392600 | 909
Acquisition of SRR eqpt. Personal protective gears & other facilities, materials, supplies and maintenance of evacuation |  | 204800 | [14 empty] | 188000 | 16800
center | [16 empty] | 188000 | 6000 | 732
[18 empty] | 10800 | 859
Purchase of 1 unit Photocopying machine |  | 139380 | [15 empty] | 139380 | 155
Purchase of 3 units computer printer |  | 0
Fogging and preventive measures against dengue |  | 0
Purchase of 1 unit brand new rescue vehicle |  | 0
Purchase of 2 units brand new Multi-purpose vehicle |  | 0
Purchase of 1 unit brand new Patient Transport vehicle |  | 0
Disaster Response, Rehabilitation and Recovery
Quick Response Fund | 1620100 | [7 empty] | 149100 |  | 710000 | 325000 |  |  |  |  | 436000
[11 empty] | 215000 | [5 empty] | 436000
495000
Provision of basic needs of evacuees, responders & other staff on-duty (food, clothing, shelter, medicines & others) |  | 0
& other services
Fuel & oil for disaster response, relief operations, assessment of infras, agriculture, |  | 36149.8 | [6 empty] | 6847.9 | 3122.8 | 26179.1
fishery & livestock & other damages & other services
[9 empty] | 2431.2 |  | 11147.2
[9 empty] | 2603.2 |  | 15031.9
1813.5
Conduct of Nutrition in Emergencies Program |  | 0
Cash for work program every after calamities |  | 948600 | [15 empty] | 948600
[18 empty] | 22100 | 175
[18 empty] | 22100 | 176
[18 empty] | 32300 | 240
[18 empty] | 22100 | 241
[18 empty] | 22100 | 242
[18 empty] | 22100 | 246
[18 empty] | 22100 | 247
[18 empty] | 22100 | 339
22100
22100
22100
22100
[18 empty] | 22100 |  | …
22100
20400
22100
30600
22100
22100
22100
20400
22100
22100
22100
22100
22100
22100
22100
22100
22100
22100
22100
30600
20400
22100
22100
22100
22100
22100
22100
20400
22100
Infrastructure rehabilitaion- rehab/repair/maintenance of calamity & disaster damages |  | 0
Gravelling of road shoulders & backfilling potholes |  | 0
Stockpiling of gravel and sand for regravelling of roadshoulders and backfilling potholes |  | 0
Agricultural rehabilitation program for Agriculture, Fishery & Livestock |  | 1379601 | [12 empty] | 469601 |  |  | 910000 | 668
469601
Emergency Shelter Assistance |  | 51000 | [15 empty] | 51000 | 480-483,492,493
Repair & Maintenance of Vehicles, heavy equipt, machineries & other SRR equipments |  | 0
Total Utilization | 1620100 | 6044603.45
Unutilized Balance | 11195351.88 | 86532675.71 |  |  |  | 97728027.59
Prepared by: | Certified Correct: |  |  | Approved by:
ARVIN FRANCIS N. LUMANG | FLORIDA S. CADANO |  |  | ENGR. ALBERT D. CHUA
CDRRMO | City Accountant |  |  | City Mayor
Note on O33: Adjustment from the month of May (error in input of amount) the amount of 5,156 to 5,165
Note on P38: change amount from 22100 to 20400
Note on Q38: change amount 22100 to 18700
Note on Q41: CGB: change amount 22100 to 20400
Note on Q42: CGB: change amount 22100 to 20400
Note on Q44: CGB: change amount 22100 to 5100
Note on P45: change amount 34000 to 32300
Note on Q45: changhe amount 22100 to 20400
Note on P51: change amount 22100 to 20400
Note on P54: change amount 30600 to 27200
Note on P55: change amount 22100 to 20400
Note on P65: CGB: change amount 22100 to 20400
Note on P66: change amount 22100 to 18700
Note on T126: change amount 20400 to 22100
Note on T152: chanege amount 22100 to 20400

## SEF 4TH QTR
Annex B
SEF Budget Accountability Form No. 1
REPORT of SEF UTILIZATION
For the Quarter Ending December 2022 | [6 empty] | JANUARY | FEBRUARY | MARCH | APRIL | MAY |  | JUNE | JULY |  | AUGUST |  | SEPTEMBER |  | OCTOBER |  | NOVEMBER |  | DECEMBER
City of Batac, Ilocos Norte
Receipt from SEF |  |  |  | P | 14825791.75
Less : |  | DISBURSEMENTS (broken down down by expense class and
by object of expenditures)
|  | Personal Services |  |  | 0
0
0
Maintenance and Other Operating Expenses
|  | Agricultural & Marine Supplies for Distribution | 1-04-02-050 |  | 290475 | [19 empty] | 290475
[24 empty] | 200-2022-12-002 | 33075
[24 empty] | 200-2022-12-005 | 257400
|  | Textbooks & Instructional Mat'l for Distribution | 1-04-02-070 |  | 576000 | [19 empty] | 576000
[24 empty] | 200-2022-12-006 | 576000
|  | Other Supplies and Materials for Distribution | 1-04-02-990 |  | 21800 | [19 empty] | 21800
[24 empty] | 200-2022-12-003 | 21800
|  | Telephone Expenses | 5-02-05-020 |  | 1980495 | [6 empty] | 198495 |  |  | 445500 |  | 222750 |  | 222750 |  | 222750 |  | 222750 |  | 445500
[11 empty] | 200-2022-05-001 | 198495 |  | 200-2022-07-001 | 24255 | 200-2022-08-001 | 222750 | 200-2022-09-002 | 222750 | 100-2022-10-001 | 222750 | 200-2022-11-001 | 222750 | 200-2022-12-001 | 222750
[14 empty] | 200-2022-07-002 | 198495 | [8 empty] | 200-2022-12-008 | 222750
[14 empty] | 200-2022-07-003 | 222750
|  | Repair and Maintenance - Machinery and Eqpt. | 5-02-13-050 |  | 269093.42 | [13 empty] | 269093.42
[18 empty] | 200-2022-09-001 | 269093.42
Capital Outlays
|  | Information & Communication Technology Eqpt. | 1-07-05-030 |  | 2273370 | [15 empty] | 2273370 |  |  |  | 0
[20 empty] | 100-2022-10-002 | 1831500
[20 empty] | 100-2022-10-002 | 441870
|  | Property & Equipment for Distribution | 1-04-02-090 |  | 3099600 | [19 empty] | 3099600
[24 empty] | 200-2022-12-004 | 40000
[24 empty] | 200-2022-12-004 | 120000
[24 empty] | 200-2022-12-004 | 29000
[24 empty] | 200-2022-12-004 | 50000
[24 empty] | 200-2022-12-007 | 2758000
[24 empty] | 200-2022-12-007 | 102600
|  | Other Supplies and Materials for Distribution | 1-04-02-990 |  | 27750 | [19 empty] | 27750
[24 empty] | 200-2022-12-004 | 2250
[24 empty] | 200-2022-12-004 | 25500
|  | Financial Expenses |  |  | 0
0
0
| Sub-total |  |  |  | 8538583.42
Balance |  |  |  | P | 6287208.33
[12 empty] | 198495 |  |  | 445500 |  | 222750 |  | 491843.42 |  | 2496120 |  | 222750 |  | 4461125
Prepared by:
FLORIDA S. CADANO
City Accountant
Appoved by:
ENGR. ALBERT D. CHUA
LCE, Chairman, LSB

## BID RESULTS
FDP Form 10a-Bid Results on Goods & Services
Republic of the Philippines
GOODS & SERVICES BID-OUT
CITY OF BATAC
FOURTH QUARTER 2022
OCTOBER TO DECEMBER
No. | BID ID No. | Name of Project | Approved Budget for Contract (In Php) | Winning Bidder | Name of Supplier | Address of Bidder | Bid Amount (In Php) | Date of Bidding | Pre-Proc Conference | Pre-bid Conference
1 | 9005795 | PURCHASE OF VARIOUS OFFICE SUPPLIES OF DIFFERENT OFFICES FOR THE 3RD & 4TH QUARTER 2022 | 4754351 | NH ROVI'S GENERAL MERCHANDISE | MR. BONNIE T. TABOR | Brgy. #2 Ablan, City of Batac, Ilocos Norte | 4719807 | October 03, 2022 | August 17, 2022 | September 21, 2022
2 | 9005821 | PURCHASE OF JANITORIAL AND CLEANIGN SUPPLIES FOR THE 3RD & 4TH QUARTER 2022 | 2244272 | ECD ENTERPRISES | ELMER C. DANCEL | #24 General Segundo Avenue, Brgy. #13. Laoag City, Ilocos Norte | 2236153 | October 03, 2022 | August 22, 2022 | September 21, 2022
3 | 9087066 | PURCHASE OF FERTILIZERS AND MATERIALS FOR DISTRIBUTION TO FARMERS IN THE CITY OF BATAC | 25209265 | STY BATAC-AGRO INDUSTRIAL TRADING | MS. EVELYN R. YAPO | Brgy. #1-N Ricarte, City of Batac, Ilocos Norte | 25173178 | October 26, 2022 | September 23, 2022 | October 14, 2022
4 | 9164629 | PURCHASE OF TILAPIA FINGERLINGS FOR DISTRIBUTION TO FISHERFOLK | 498750 | NATURE'S WEALTH TRADING | MR. EMILIO G. PERUCHO | Brgy. #8 San Vicente, Laoag City, Ilocos Norte | 498037.5 | November 04, 2022 | N/A | N/A
5 | 9165033 | PURCHASE OF OF MULTI-FUNCTION LARGE FORMAT COLOR PRINTER | 480000 | GAKKEN PHILIPPINES, INC. | MR. JAFET B. LLOBRERA | 130 GPI Bldg. Aurora Boulevard Cor A. Lake St. San Juan City, Metro Manila | 450000 | November 04, 2022 | N/A | N/A
6 | 9165084 | PURCHASE OF VETERINARY MEDICINES AND DEWORMERS (FLU KIT & VIT) FOR LIVESTOCK RAISERS | 798575 | ST. RUIZ AGRO FARM SUPPLY & GEN. MDSE. | MS. MILAGROS R. GALVEZ | Brgy. #17 San Francisco, Laoag City, Ilocos Norte | 684525 | November 04, 2022 | N/A | N/A
7 | 9165127 | PUCHASE OF UNIFORMS FOR THE INTER-HIGH SCHOOL TOURNAMENT | 483180 | JOSHUA AND CALEB GENERAL MERCHANDISE | MS. GLORIA A. ALEGAR | Brgy. #9, Sta. Angela, Laoag City, Ilocos Norte | 481980 | November 04, 2022 | N/A | N/A
8 | 9165176 | PURCHASE OF VACCINES FOR SENIOR CITIZENS | 999600 | EQA PHARMACEUTICAL PRODUCTS DISTRIBUTION | MR. CHRISTOPHER P. CALDERON | Brgy. #16 San Marcos, San Nicolas, Ilocos Norte | 999600 | November 04, 2022 | N/A | N/A
9 | 9165809 | PURCHASE OF CHRISTMAS DECORATIONS- CHRISTMAS TREE & CHRISTMAS DECORATIONS CITY HALL LOBBY | 999400 | ECD ENTERPRISES | ELMER C. DANCEL | #24 General Segundo Avenue, Brgy. #13. Laoag City, Ilocos Norte | 995000 | November 04, 2022 | N/A | N/A
10 | 9177202 | PURCHASE OF MANUAL FERTILIZER APPLICATOR FOR DISTRIBUTION TO CORN FARMERS | 500000 | STY BATAC-AGRO INDUSTRIAL TRADING | MS. EVELYN R. YAPO | Brgy. #1-N Ricarte, City of Batac, Ilocos Norte | 498000 | November 09, 2022 | N/A | N/A
11 | 9177212 | PURCHASE OF SUPPLIES AND MATERIALS FOR CITY PLANT NURSERY, TECHNO DEMO ON ORGANIC VEGETABLE PRODUCTION AND FOR DISTRIBUTION TO FARMERS AND INDIGENT FAMILIES | 710415 | STY BATAC-AGRO INDUSTRIAL TRADING | MS. EVELYN R. YAPO | Brgy. #1-N Ricarte, City of Batac, Ilocos Norte | 707315 | November 09, 2022 | N/A | N/A
12 | 9165739 | PURCHASE OF LEARNING MATERIALS FOR CHILDREN AND CHILD DEVELOPMENT CENTERS | 1202625 | MAGILAS DISTRIBUTION AND TRADING | MS. ABIGAIL E. PASCUAL | Brgy. #16 San Marcos, San Nicolas, Ilocos Norte | 1199250 | November 16, 2022 | N/A | November 04, 2022
13 | 9165761 | PURCHASE OF EDUCATIONAL SUPPLIES AND MATERIALS FOR PUPILS AND STUDENTS OF THE PUBLIC SCHOOLS OF THE CITY OF BATAC | 23759778 | NH ROVI'S GENERAL MERCHANDISE | MR. BONNIE T. TABOR | Brgy. #2 Ablan, City of Batac, Ilocos Norte | 19205009.4 | November 16, 2022 | October 12, 2022 | November 04, 2022
14 | 9165789 | PURCHASE OF CHRISTMAS LIGHTS AND STREET LAMPS | 1998000 | ROLREN'S LANTERN AND GENERAL MERCHANDISE | MR. ERETZ ISRAEL A. QUIAMBAO | 11th Avenue, Unisite Subd., Del Pilar, San Fernando City, Pampanga | 1991565 | November 16, 2022 | N/A | November 04, 2022
15 | 9177170 | PURCHASE OF FERTILIZERS FOR DISTRIBUTION TO FARMERS IN THE CITY OF BATAC | 9997145 | STY BATAC-AGRO INDUSTRIAL TRADING | MS. EVELYN R. YAPO | Brgy. #1-N Ricarte, City of Batac, Ilocos Norte | 9985115 | November 21, 2022 | November 07, 2022 | November 09, 2022
16 | 9177187 | PURCHASE OF 2 SETS HIGH VOLUME, LOW SPEED FAN FOR THE ICC WITH INSTALLATION | 1700000 | 3A'S ONE MARKETING INTERNATIONAL CORPORATION | MS. MARIA TERESA TELMOSA | #118 Ligaya St., 7th Ave. East, Caloocan City, Metro Manila | 1695000 | November 21, 2022 | N/A | November 09, 2022
17 | 9231409 | PURCHASE OF SUPPLEMENTARY READING MATERIALS | 577600 | MAGILAS DISTRIBUTION AND TRADING | MS. ABIGAIL E. PASCUAL | Brgy. #16 San Marcos, San Nicolas, Ilocos Norte | 576000 | November 23, 2022 | N/A | N/A
18 | 9239227 | PURCHASE OF LAPTOP AND MULTI-FUNCTION PRINTER | 2905000 | MSTRIT.COM COMPUTER AND MARKETING SERVICES | JADE M. PARADO | Brgy. #14 P Acosta St., Laoag City, Ilocos Norte | 2860600 | December 07, 2022 | November 07, 2022 | November 25, 2022
19 | 9294455 | PURCHASE OF GROCERY ITEMS FOR THE CHRISTMAS GIFT GIVING ACTIVITY OF PWDs | 849660 | NEW JAVIER TRADING CORPORATION | MR. ESTEBAN DANILO C. JAVIER | JTC Mall, National Highway, Balaleng, Bantay, Ilocos Sur | 848836.8 | December 07, 2022 | N/A | N/A
20 | 9294490 | PURCHASE OF MULTI-FUNCTION LARGE FORMAT COLOR PRINTER | 960000 | GAKKEN PHILIPPINES, INC. | MR. JAFET B. LLOBRERA | 130 GPI Bldg. Aurora Boulevard Cor A. Lake St. San Juan City, Metro Manila | 900000 | December 07, 2022 | N/A | N/A
21 | 9294524 | PURCHASE OF MULTI-FUNTION PRINTER (PLOTTER) | 500000 | GAKKEN PHILIPPINES, INC. | MR. JAFET B. LLOBRERA | 130 GPI Bldg. Aurora Boulevard Cor A. Lake St. San Juan City, Metro Manila | 450000 | December 07, 2022 | N/A | N/A
22 | 9256811 | PURCHASE OF CONSTRUCTION MATERIALS FOR FLUE CURING BARN | 7464568.33 | A.B. CASIANO GRAVEL & SAND CONSTRUCTION SUPPLY | MS. APRIL JOYCE Y. SINFUEGO | Brgy. #2 San Baltazar, San Nicolas, Ilocos Norte | 7463361.6 | December 12, 2022 | November 09, 2022 | November 29, 2022
23 | 9256823 | PURCHASE OF GROCERY ITEMS FOR THE PANAGRIRINNANUD TI PASKUA 2022 | 22000000 | NEW JAVIER TRADING CORPORATION | MR. ESTEBAN DANILO C. JAVIER | JTC Mall, National Highway, Balaleng, Bantay, Ilocos Sur | 21990100 | December 12, 2022 | Ocotber 28, 2022 | November 29, 2022
24 | 9326752 | PURCHASE OF GROCERY ITEMS FOR THE CHRISTMAS FESTIVAL AND GIFT GIVING FOR SENIOR CITIZENS | 600000 | NEW JAVIER TRADING CORPORATION | MR. ESTEBAN DANILO C. JAVIER | JTC Mall, National Highway, Balaleng, Bantay, Ilocos Sur | 598425 | December 16, 2022 | N/A | N/A
| 8770271 | PURCHASE OF LABORATORY SUPPLIES AND REAGENTS FOR THE THIRD AND FOURTH QUARTER OF 2022 | 1223522 | BDSCIENTIA MEDICAL AND DIAGNOSTIC SUPPLIES | GRACE MAY F. DALISAY | Lot 2A Gladiola Street, Upper Q.M., Baguio City | 1221870 | July 11, 2022 | - | June 29, 2022
| 8797741 | PURCHASE OF MEDICINES FOR THE USE OF CITY HEALTH OFFICE FOR THE 3RD AND 4TH QUARTER 2022 | 7982087 | ABM - A BUILDER MARKETING | ALDRIN B. MAGAOAY | BGRY.7-B 3 B GIRON ST., LAOAG CITY, ILOCOS NORTE | 7976387 | July 20, 2022 | June 10, 2022 | July 08, 2022
| 8797752 | PURCHASE OF VARIOUS MEDICAL AND DENTAL SUPPLIES AND VACCINES FOR THE USE OF CITY HEALTH OFFICE FOR THE 3RD AND 4TH QUARTER OF 2022 | 11633547 | ABM - A BUILDER MARKETING | ALDRIN B. MAGAOAY | BGRY.7-B 3 B GIRON ST., LAOAG CITY, ILOCOS NORTE | 11630962 | July 20, 2022 | June 10, 2022 | July 08, 2022
| 8915378 | PURCHASE OF PERSONAL PROTECTIVE SUPPLIES FOR USE OF VARIOUS OFFICES | 2213310 | ABM - A BUILDER MARKETING | ALDRIN B. MAGAOAY | BGRY.7-B 3 B GIRON ST., LAOAG CITY, ILOCOS NORTE | 2209701 | August 31, 2022 | July 04, 2022 | August 19, 2022
| 8915406 | PURCHASE OF HEAVY DUTY MECHANICAL WEIGH BEAM PLATFORM WITH HEIGHT | 1800000 | HEALTHPRO GENERICS & MEDICAL SUPPLIES | JENNIFER S. ANTONIO | P. GOMEZ ST. BRGY.23 SAN MATIAS, LAOAG CITY, ILOCOS NORTE | 1788000 | August 31, 2022 | - | August 19, 2022
x-x-x-x-x-x-x-x-x
We certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
MARLON F. SORIA WILMA T. ICUSPIT NORALYN I. MANAHAN HILARION G. NALUPTA NORIEL BENSON R. TABUNAN
BAC CHAIRMAN BAC VICE CHAIRMAN BAC MEMBER BAC MEMBER BAC MEMBER