## SPP 2021-03
CITY GOVERNMENT OF BATAC
SUPPLEMENTAL PROCUREMENT PLAN 2021-03
Code (PAP) | Procurement Project | PMO/ End-User | Is this an Early Procurement Activity? (Yes/No) | Mode of Procurement | Schedule for Each Procurement Activity |  |  |  | Source of Funds | Estimated Budget (PhP) |  |  | Remarks (brief description of Project)
[5 empty] | Advertisement/Posting of IB/REI | Submission/Opening of Bids | Notice of Award | Contract Signing |  | Total | MOOE | CO
| PURCHASE OF FOOD PACKS FOR THE PANAGRIRINNANUD Tl PASKUA (GIFT GIVING) | CSWDO | No | Competetive Bidding | November 4, 2021 | November 24, 2021 | December 7, 2021 | December 10, 2021 | GoP | 14400000 | 14400000 |  | AO 5SP 2021-03; Additional Funding & Annual Budget 2021
| PURCHASE OF FUEL FOR THE FUEL SUBSIDY PROGRAM TO FARMERS | Office of the City Agriculturist | No | Competetive Bidding | December 2, 2021 | December 22, 2021 | December 28, 2021 | December 29, 2021 | GoP | 5000000 | 5000000 |  | AO 5SP 2021-03
| PURCHASE OF ALUMINUM GLASS WINDOW AND DOOR FOR THE TWO ADDITIONAL ROOMS OF BRGY. BILLOCA BARANGAY HALL | City Engineering Office | No | Negotiated Procurement-Small Value Procurement | December, 2021 |  |  |  | GoP | 200000 |  | 200000 | AO 5SP 2021-03
| PURCHASE OF BENCHES FOR DISTRIBUTION TO DIFFERENT TRICYCLE TERMINAL | CSWDO | No | Competetive Bidding | November 16, 2021 | November 24, 2021 | December 7, 2021 | December 9, 2021 | GoP | 774000 | 774000 |  | AO 5SP 2021-03
| PURCHASE OF BASKETBALL BALL AND BASKETBALL BOARDS | OTM | No | Competetive Bidding | November 16, 2021 | December 6, 2021 | December 17, 2021 | December 20, 2021 | GoP | 1132000 | 1132000 |  | AO 5SP 2021-03
| PURCHASE OF 10 UNITS SOUND SYSTEM FOR SCHOOLS AND BARANGAYS | GSO | No | Competetive Bidding | October to December 2021 |  |  |  | GoP | 1000000 |  | 1000000 | AO 5SP 2021-03
| PURCHASE OF LAPTOPS FOR VARIOUS BARANGAYS | CSWDO/CHO | No | Competetive Bidding | October to December 2021 |  |  |  | GoP | 2150000 |  | 2150000 | AO 5SP 2021-03
| INSTALLATION OF WATER SYSTEMS DISTRIBUTION LINES TO HOUSEHOLDS OF BARANGAY MAIPALIG | City Engineering Office | No | Competetive Bidding | October to December 2021 |  |  |  | GoP | 900000 |  | 900000 | AO 5SP 2021-03
| INSTALLATION/CONSTRUCTION OF BOX CULVERT/CROSS DRAINAGE | City Engineering Office/Office of the City Agriculturist | No | Competetive Bidding | October to December 2021 |  |  |  | GoP | 600000 |  | 600000 | AO 5SP 2021-03
| FOOD ACCOMODATION FOR COVID-19 PERSONS UNDER MONITORING STAYING IN THE CITY FACILITIES | City Health Office | No | Emergency Purchase | October to December 2021 |  |  |  | GoP | 3000000 | 3000000 |  | AO 5SP 2021-03
| PURCHASE OF HYGIENE KITS | City Health Office | No | Competetive Bidding | October 7, 2021 | October 27, 2021 | November 9, 2021 | November 15, 2021 | GoP | 5000000 | 5000000 |  | AO 5SP 2021-03
| PURCHASE OF ASCORBIC ACID WITH ZINC | Various Offices | No | Competetive Bidding | November 11, 2021 | December 1, 2021 | December 15, 2021 | December 17, 2021 | GoP | 5000000 | 5000000 |  | AO 5SP 2021-03
| Prepared by: |  | Noted by: | [5 empty] | Approved by:
| CHRISTINE MAE M. BAYANGGOS |  |  | MARLON F. SORIA | [6 empty] | ENGR. ALBERT D. CHUA
| Acting Head, BAC-Secretariat |  |  | BAC Chairman | [6 empty] | City Mayor
| PURCHASE OF FOOD PACKS FOR DISTRIBUTION TO VACCINATED INDIVIDUALS RESIDING AT THE CITY OF BATAC | CPDO/CHO/ CSWDO | No | Emergency Purchase | December, 2021 |  |  |  | GoP | 10000000 | 10000000 |  | Resolution No.5 SP 2021-262
| CHRISTMAS FESTIVAL AND GIFT GIVING TO SENIOR CITIZENS (ADDITIONAL FUNDING) | CSWDO | No | Competetive Bidding | October to December 2021 |  |  |  | GoP | 3777000 | 3777000 |  | AO 5SP 2021-03
| PERSON WITH DISABILITY-CHRISTMAS FESTIVAL AND GIFT GIVING TO SENIOR CITIZENS (ADDITIONAL FUNDING) | CSWDO | No | Competetive Bidding | October to December 2021 |  |  |  | GoP | 200000 | 200000 |  | AO 5SP 2021-03
[10 empty] | 53133000 | 48283000 | 4850000
| Prepared by: |  | Noted by: | [5 empty] | Approved by:
| CHRISTINE MAE M. BAYANGGOS |  |  | MARLON F. SORIA | [6 empty] | ENGR. ALBERT D. CHUA
| Acting Head, BAC-Secretariat |  |  | BAC Chairman | [6 empty] | City Mayor