## 2nd qtr
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 2nd QUARTER CY 2022
FUNCTION/PROGRAM PROJECT ACTIVITY |  |  | LOCATION/COVERAGE | TOTAL COST | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | NO. OF EXTENSIONS, IF ANY | REMARKS
[19 empty] | % OF COMPLETION | TOTAL COST INCURRED
SOCIAL DEVELOPMENT
| Recovery Assistance to Hog Raisers affected to African Swine Fever (ASF) |  | All Barangays | 10000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Support to COVID-19 related PPAs |  | All Barangays | 20000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Sub-total |  |  | 30000000 | [15 empty] | 0
ECONOMIC DEVELOPMENT
| Concreting of Farm-to-Market Road |  |  | 40261034.8 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Road Widening |  |  | 500000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Additional Funding for the Construction of Sumader SWIP |  | Brgy. Sumader | 20000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Rehabilitation of Spillway |  |  | 2000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Improvement of small water impounfding | [16 empty] | Jan.-Dec. 2022 |  | 0
| Concreting of irrigation Canal |  |  | 5000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Rehabilitation /Excavation of Small Farm Reservior (SFR) |  |  | 2000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Construction and rehabilitation of Diversion Dam |  |  | 5000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Development of Public Market | [16 empty] | Jan.-Dec. 2022 |  | 0
| Installation of Cargo Lift (3 units) |  |  | 5000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Installation of Elecrical Wirings for Bldg. 1-6 |  |  | 3000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Sub-total |  |  | 82761034.8 | [15 empty] | 0
ENVIRONMENTAL MANAGEMENT
Solid Waste management Program
| Upkeeping & preservation of the City Waste Disposal Site |  |  | 500000 | [13 empty] | Jan.-Dec. 2022 | 95.85% | 479240.66
| Construction of Slope Protection & Drainage System along the Garbage pond & Concreting of Road Network |  |  | 8000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Purchase of Dumptruck |  |  | 5000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Construction of Roadway Slope Protection |  |  | 20000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Dredging of Waterways (rivers/ creeks/ canals) |  |  | 2000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Sub-total |  |  | 35500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1.35% | 479240.66
| TOTAL SPA-20% DF |  |  | 148261034.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | 0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
|  | WILMA T. ICUSPIT | [16 empty] | ENGR. ALBERT D. CHUA
|  | City Budget Officer | [16 empty] | City Mayor

## cash advance
FDP Form 12 - Unliquidated Cash Advances
UNLIQUIDATED CASH ADVANCES
As of JUNE 30, 2022
City of Batac, Ilocos Norte - General Fund
Name of Debtor | Amount |  |  |  | Amount Due
(In alphabetical order) | Balance |  | Date Granted | Purpose | Current |  |  | Past Due
[5 empty] | Less than 30 days | 31-90 days | 91-365 days | Over 1 year | Over 2 years | 3 years and above
Bismark Angelo A. Quidang | 40589 |  | 2022-06-09 | Travel | 40589
Donnel C. Binala | 5100 |  | 2022-06-13 | Travel | 5100
Noralyn I. Manahan | 3300 |  | 2022-06-17 | Travel | 3300
James A. Espiritu | 3300 |  | 2022-06-17 | Travel | 3300
Tristan Melecia D. Advincula | 3300 |  | 2022-06-17 | Travel | 3300
Merlyn T. Gorospe | 3300 |  | 2022-06-17 | Travel | 3300
Noriel Benson R. Tabunan | 3300 |  | 2022-06-17 | Travel | 3300
Michael John D. Tadifa | 3300 |  | 2022-06-17 | Travel | 3300
Angelica S. Yumul | 3300 |  | 2022-06-17 | Travel | 3300
Rowelle B. Gabay | 22700 |  | 2022-06-28 | Travel | 22700
Regie M. Viernes | 7700 |  | 2022-06-28 | Travel | 7700
Ricarte A. Calacal, Jr. | 7700 |  | 2022-06-28 | Travel | 7700
TOTAL | 106889 | 0 |  |  | 106889 | 0 | 0 | 0 | 0 | 0
We hereby certify that we have reveiwed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
FLORIDA S. CADANO | [5 empty] | ENGR. ALBERT D. CHUA
City Accountant | [5 empty] | City Mayor
0

## manpower
FDP Form 13 - Manpower Complement
MANPOWER COMPLEMENT
Republic of the Philippines
CITY OF BATAC
As of June 30, 2022
Nature of Apppointment or Employment |  | Number | Compensation and Other Benefits |  | Total
|  |  | Salaries and Wages | Other Monetary Benefits
I. | Permanent | 254 | 40296602.6 | 21606121.02 | 61902723.62
II. | Contractual/Casual | 72 | 4471328.21 | 2989714.61 | 7461042.82
III. | Job Order/Contract of Service | 162 | 10377527.98 |  | 10377527.98 | 69363766.44
Grand Total |  | 488 | 55145458.79 | 24595835.63 | 79741294.42
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information
contained in this document.
4308008.66
MARLON F. SORIA |  |  | FLORIDA S. CADANO |  | ENGR. ALBERT D. CHUA |  | 6069519.32
Human Resource Management Officer |  |  | Accountant |  | City Mayor |  | 10377527.98
Note:
1. Contractual Personnel are those whose employment in the government is in accordance with a special contract to undertake a specific work or job, requiring special
or technical skills not available in the employing agency, to be accomplished within a specific period which in no case shall exceed one year, and performs or accomplishes
the specific work or job, under his own responsibility with a minimum of direction and supervision from the hiring agency. (Source: PRESIDENTIAL DECREE No. 807
October 6, 1975)
2. Contract of Services/Job Orders are employees whose services rendered are not considered governments services and do not enjoy the benefits enjoyed by government
employees. The job order covers piece work or intermittent job of short duration not exceeding six months on a daily basis. (Source: Omnibus Rules Implementing Book V
of E.D. No. 292 and Other Pertinent Civil Service Laws)

## 2ND BID - OUT
FDP Form 10a-Bid Results on Goods & Services
Republic of the Philippines
GOODS & SERVICES BID-OUT
CITY OF BATAC
Second Quarter 2022
APRIL TO JUNE
No. | Reference No. | Item Description | Approved Budget for Contract (In Php) | Winning Bidder | Name of Supplier | Address of Bidder | Bid Amount (In Php) | Date of Bidding | Pre-Proc Conference | Pre-bid Conference
1 | 8599423 | PROVISION OF ANTI-PNEUMONIA AND ANTI-FLU VACCINES | 1295000 | VAXSHOT PHARMACEUTICAL | CHRISTOPHER P. CALDERON | 11 Heroes Avenue Kalayaan Village, Quebiawan, City of San Fernando, Pampanga | 1295000 | 2022-05-04 | 2022-03-23 | 2022-04-20
2 | 8599440 | PROVISION OF FREE VITAMIN C WITH ZINC AND MULTI-VITAMINS | 5325300 | ABM-A BUILDER MARKETING | ALDRIN B. MAGAOAY | BGRY.7-B 3 B GIRON ST., LAOAG CITY, ILOCOS NORTE | 5324572.5 | 2022-05-04 | 2022-03-23 | 2022-04-20
3 | 8673254 | PURCHASE OF VARIOUS MEDICINES AND MEDICAL SUPPLIES FOR THE BARANGAY MEDICAL MISSION | 500000 | HEALTHPRO GENERICS & MEDICAL SUPPLIES | JENNIFER S. ANTONIO | P. GOMEZ ST. BRGY.23 SAN MATIAS, LAOAG CITY, ILOCOS NORTE | 482760 | 2022-05-30 | - | -
4 | 8712346 | PROCUREMENT OF MEALS FOR THE INAUGURATION | 450000 | MARGARITA'S CATERING | LINABEL RUTH C. SAGUN | Brgy. #2 Ablan, City of Batac, Ilocos Norte | 448650 | 2022-06-08 | - | -
5 | 8682274 | PURCHASE OF ONE UNIT HEMATOLOGY ANALYZER FOR THE CITY HEALTH OFFICE-CLINICAL LABORATORY | 1500000 | BDSCIENTIA MEDICAL AND DIAGNOSTIC SUPPLIES | GRACE MAY F. DALISAY | Lot 2A Gladiola Street, Upper Q.M., Baguio City | 1480000 | 2022-06-13 | - | June 01, 2022
6 | 8682500 | PURCHASE OF 33 UNITS LAPTOP | 2640000 | MSTRIT.COM COMPUTER AND MARKETING SERVICES | JADE M. PARADO | Brgy. #14 P Acosta St., Laoag City, Ilocos Norte | 2273370 | 2022-06-13 | March 23, 2022 | June 01, 2022
7 | 8712346 | PROCUREMENT OF MEALS FOR THE INAUGURATION | 450000 | MARGARITA'S CATERING | LINABEL RUTH C. SAGUN | Brgy. #2 Ablan, City of Batac, Ilocos Norte | 448650 | June 08, 2022 | - | -
8 | 8730211 | PURCHASE OF MEDALS | 757200 | GREGMAN'S GENERAL MERCHANDISE | NORMA M. SAMSON | 2119 Zamora St. San Roque, Tarlac City | 754676 | June 15, 2022 | - | -
9 | 8741338 | PURCHASE OF SPARE PARTS FOR THE REPAIR OF HEAVY EQUIPMENT | 1430000 | JPLC TRADING | ANGELITO P. CARRIEDO | 114 Ligaya St. 7th Ave., Barangay 122, District 2, Caloocan City | 1420000 | June 29, 2022 | - | June 17, 2022
| 8770271 | PURCHASE OF LABORATORY SUPPLIES AND REAGENTS FOR THE THIRD AND FOURTH QUARTER OF 2022 | 1223522 | BDSCIENTIA MEDICAL AND DIAGNOSTIC SUPPLIES | GRACE MAY F. DALISAY | Lot 2A Gladiola Street, Upper Q.M., Baguio City | 1221870 | July 11, 2022 | - | June 29, 2022
| 8797741 | PURCHASE OF MEDICINES FOR THE USE OF CITY HEALTH OFFICE FOR THE 3RD AND 4TH QUARTER 2022 | 7982087 | ABM - A BUILDER MARKETING | ALDRIN B. MAGAOAY | BGRY.7-B 3 B GIRON ST., LAOAG CITY, ILOCOS NORTE | 7976387 | July 20, 2022 | June 10, 2022 | July 08, 2022
| 8797752 | PURCHASE OF VARIOUS MEDICAL AND DENTAL SUPPLIES AND VACCINES FOR THE USE OF CITY HEALTH OFFICE FOR THE 3RD AND 4TH QUARTER OF 2022 | 11633547 | ABM - A BUILDER MARKETING | ALDRIN B. MAGAOAY | BGRY.7-B 3 B GIRON ST., LAOAG CITY, ILOCOS NORTE | 11630962 | July 20, 2022 | June 10, 2022 | July 08, 2022
| 8915378 | PURCHASE OF PERSONAL PROTECTIVE SUPPLIES FOR USE OF VARIOUS OFFICES | 2213310 | ABM - A BUILDER MARKETING | ALDRIN B. MAGAOAY | BGRY.7-B 3 B GIRON ST., LAOAG CITY, ILOCOS NORTE | 2209701 | August 31, 2022 | July 04, 2022 | August 19, 2022
| 8915406 | PURCHASE OF HEAVY DUTY MECHANICAL WEIGH BEAM PLATFORM WITH HEIGHT | 1800000 | HEALTHPRO GENERICS & MEDICAL SUPPLIES | JENNIFER S. ANTONIO | P. GOMEZ ST. BRGY.23 SAN MATIAS, LAOAG CITY, ILOCOS NORTE | 1788000 | August 31, 2022 | - | August 19, 2022
x-x-x-x-x-x-x-x-x
We certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
MARLON F. SORIA WILMA T. ICUSPIT NORALYN I. MANAHAN HILARION G. NALUPTA NORIEL BENSON R. TABUNAN
BAC CHAIRMAN BAC VICE CHAIRMAN BAC MEMBER BAC MEMBER BAC MEMBER

## TRUST FUND UTILIZATION
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 2nd QUARTER, CY 2022
Province, City or Municipality: BATAC CITY
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | Balance |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date |  | Previous Balance
Philhealth Capitation |  | 12906684.2 | 2011-2017 |  | 73.03% | 9426042.97 | 3480641.23 | 7649160.34 |  | ongoing | 3480641.23
Animal Bite Treatment Package |  | 1130000 | February 2017 |  | 99.5% | 1124557 | 5443 | 752657 |  | ongoing | 5443
TB-DOTS |  | 399975 | 2015-2017 |  | 68.48% | 273901 | 126074 | 273901 |  | ongoing | 126074
HCI Charges |  | 574675 | 2018-2019 |  | 0% | [5 empty] | 574675
Transfer for the Rehabilitation of Small Scale Irrigation Project | Brgy. Camandingan, Batac City, I.N. | 3000000 | June 13, 2014 delivery of materials |  | 100% | 2284116.5 |  | 2245966.5 |  | liquidated with refund of 715,883.50 Check # 638708 | 715883.5
Construction of Sumader SWIP | Brgy. Sumader, Batac City, I.N. | 29254500 |  |  | 63.09% | 29254500 | 0 |  |  | Second Billing paid under Voucher No. 100-2021-03-1161; Check No. 794803 | 0
Fund transfer for the conversion of existing Day Care Centers to Child Development Centers |  | 1000000 |  |  | 100% | 735206 | 264794 | 735206 |  | Fully liquidated, balance of P264,794.00 refunded under check no. 638775 | 264794
Technology Adoption & Commercialization of Hawaiian Ginger & Turmeric | Baligat, Camandingan, San Pedro | 2103093 | February 2017 |  | 100% | 1791754.88 | 853340.52 | 1782879.08 |  | Balance refunded under Voucher No. 100-2021-12-3856; Check No. 868222 | 311338.12
Rehabilitation of Baoa Diversion Dam | Baoa East, Baoa West | 1440000 | Receipt of Fund-July 2017 |  | 100% |  | 1440000 |  |  | with liquidating damages in the amount of P19,707.24 | 1440000
Establishment of Adolescent Friendly Health Facilities |  | 50000 | February 2018 |  | 100% | 50000 |  |  |  | liquidated | 0
Technology Adoption & Commercialization of Hawaiian Ginger & Turmeric | Baligat, Camandingan, San Pedro | 2103093 | Receipt of Fund December 2018 |  | 50% |  |  |  |  | Balance refunded under Voucher No. 100-2021-12-3856; Check No. 868222 | 2103093
Funding Support of Safe Closure and Rehabilitation Plan (SCRP) of Open and Controlled Dumpsite (Perimeter Fence) | Brgy. 31 Camandingan | 1822247.42 | Receipt of Fund December 2018 |  | 100% | 1822247.42 |  |  |  | First and Final Billing paid under Check No. 794602 in the amount of 1,822,247.42; with liquidation report | 0
Proposed Riverfront Promenade | Brgy. Ablan & Valdez | 7077100 | Receipt of Fund-March 2019 |  | 100% | 7042223.44 | 34876.56 |  |  | Liquidated: Final Billing paid under Voucher No. 100-2021-09-2728; Check No. 796089; Refund of 34,876.56 paid under Voucher No. 100-21-09-2806; Check No. 796091 | 34876.56
Riverfront Promenade Phase 2 | Brgy. Ablan & Valdez | 13750201 | Receipt of Fund-December 2019 | [6 empty] | For First Billing | 13750201
Performance Challenge Fund: |  | 3500000 | Receipt of Fund-December 2019 |  | 100% | 3490000 |  |  |  | Liquidated: First and Final Billing paid under Voucher No. 300-21-07-018; Check No. 688007; Refund of 10,000 paid under Voucher No. 300-2021-07-19; Check No. 688008 | 10000
Share of the City-2012 7171 Excise Tax- | [10 empty] | 0
| 22 rural barangays | 34500000 | October,2015 |  | 100% | 34167234.31 | 332765.69 | 34167234.31 |  | completed | 332765.69
Construction/Rehabilitation of Farm to Market Road | [10 empty] | 0
Share of the City-Direct shares of Congressional Districts for the 2012 | [10 empty] | 0
Excise Tax: | [10 empty] | 0
Farm to Market Road | rural barangays | 15000000 | November,2015 |  | 100% | 14280464.15 | 719535.85 | 14280464.15 |  | completed | 719535.85
Purchase of Various Equipment | 43 barangays | 40745187 | November,2015 |  | 92.15% | 37546995 | 12597192 | 37546995 |  | ongoing | 3198192
Buy -back and Other Marketing | [10 empty] | 0
Programs for Critical Alterna- | [9 empty] | ongoing | 0
tive crops to tobacco |  | 4000000 | November,2015 |  | 89.55% | 3581998.24 | 418001.76 | 3581998.24 |  |  | 418001.76
Local Government Support Fund: | [10 empty] | 0
SALINTUBIG(Sagana at Ligtas na Tubig sa Lahat) Provision of Portable Water Supply | [9 empty] | Waiting for request of final billing from contractor | 0
| Pimentel | 500000 | 2017-10-22 |  | 100% | [5 empty] | 500000
| Maipalig | 1060000 | 2017-10-22 |  | 100% | [5 empty] | 1060000
0
FY 2020 Local Government Support Fund-Assistance to Cities (Riverfront Promenade 3) |  | 10647492 | Receipt of Fund- November 2021 | [6 empty] | For PhilGeps Posting | 10647492
DSWD-RF01 | [10 empty] | 0
Cost for Viand and Rice for 1,050 Children in the implementation of SFP CY 2017 |  | 1890000 | Receipt of Fund-September 2018 |  | 50.21% | 948991.96 | 1890000 |  |  | Fully Liquidated, with a refund of 941,008.04; Check No. 638772 | 941008.04
Fund Transfer-Social Pension 3rd Qtr |  | 1264500 | Receipt of Fund-October 2018 |  | 100% | 1264500 | 0 | 1264500 |  | liquidated | 0
Fund Transfer-Social Pension 4th Qtr |  | 1264500 | Receipt of Fund-October 2018 |  | 100% | 1264500 | 0 | 1264500 |  | liquidated | 0
ATI-RTC I | [10 empty] | 0
Funding Support for the Sustainable Community Development Through the Conduct of Series of Training Under the Extension Program fro Agri-Fisheries and National Development (Expand) or Grant System |  | 905000 | Receipt of Fund-December 27, 2018 |  | 100% | 876294.28 | 28705.72 | 111357.38 |  | liquidated with refund of 28,705.71 Check # 638717 | 28705.72
DEPARTMENT OF ENERGY | [10 empty] | 0
ER 1-94 COVID related projects of the City Government of Batac (from the DOE) | City of Batac, Ilocos Norte | 200000 | August 2020 |  | 100% | 193836 |  |  |  | According to DOE, the balance of P6,164 will be used to purchase alcohol. | 6164
DANGEROUS DRUGS BOARD | [10 empty] | 0
Financial Assistance-Dangerous Drugs Board |  | 6000000 | Receipt of Fund- December 2021 | [7 empty] | 6000000
OFFICE OF THE PRESIDENT | [10 empty] | 0
Financial Assistance to cater and address the immediate needs of the people affected by the health crisis brought about by the Corona Virus Disease (COVID-19) per approved Memorandum dated March 4, 2021 | City of Batac, Ilocos Norte | 5000000 | Receipt of Fund March 2021 |  | 100% | 4963262 |  |  |  | Liquidated with refund to Office of the President amounting to P36,738.00 under Check No. 638811 | 36738
DSWD-RO I | [10 empty] | 0
Rehabilitation of Senior Citizen Building | [9 empty] | liquidating damages in the amount of P20,809.15 | 0
Others: | [10 empty] | 0
Prizes for Most Outstanding Farmers |  | 100000 | January 2017 |  | 0% | [5 empty] | 100000
Cash Donation Support to PNCR-Ilocos Norte Chapter |  | 3000 | March 2017 |  | 0% | [5 empty] | 3000
Sustainable Development Goals-Family Based Actions for Children and their Environment in the Slims (SDG FACES) |  | 50000 | November 2017 |  | 0% |  |  |  |  | not implemented | 50000
PBSP-CHO PMDT |  | 7610 | December 2017 |  | 0% | [5 empty] | 7610
Travelling Allowance for existing BNS for 2019 |  | 56400 | Receipt of Fund-June 2019 |  | 100% | 56400 |  |  |  | completed | 0
SOCIAL AMELIORATION PROGRAM | City of Batac, Ilocos Norte | 51700000 | April 2020 |  | 100% | 51700000 |  |  |  | Fully liquidated | 0
SOCIAL PENSION for Indigent Senior Citizen for the 1st Semester of 2020 | City of Batac, Ilocos Norte | 2319000 | June 2020 |  | 100% | 2319000 |  |  |  | Fully Liquidated, with a refund of 114,000; Check No. 638768 | 0
Provision of Water Pumps (Department of Labor and Employment) | City of Batac, Ilocos Norte | 1400000 | July 2020 |  | 100% | 1399950 |  |  |  | Voucher and check of refund in the amount of P50.00 was prepared under V#300-2021-03-009; check#638783 | 50
Travelling Allowance for existing BNS for 2022 |  | 55200 | Receipt of Fund-May 23, 2022 |  | 0% | [5 empty] | 55200
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
| FLORIDA S. CADANO |  |  |  |  | ENGR. ALBERT D. CHUA
| City Accountant |  |  |  |  | City Mayor

## Q2 - 2022
FDP Form 9 - Statement of Cash Flow
(COA Form)
STATEMENT OF CASH FLOWS
For the Period Ended June 30, 2022
City of Batac, Ilocos Norte
ALL FUNDS
Cash Flows from Operating Activities:
| Cash Inflows: |  |  |  | JULY | AUG | SEPT | TOTAL
|  | Collection from Taxpayers | 45794499.1 |  | 3439015.48 | 147940480.48 | 699967.03 | 152079462.99
|  | Share from Internal Revenue Collections | 370652688 |  | 28338227 | 28338227 | 28338227 | 85014681
Other Share from National Taxes
|  | Receipts from Sale of Goods or Services | 33135056.49 |  | 4047229.68 | 3381043.18 | 3296311.72 | 10724584.58
|  | Interest Income | 1239890.73 |  | 267487.57 | 266649.18 | 262327.28 | 796464.03
|  | Other Receipts | 46090776.05 |  | 432257.56 | 4580703.73 | 587219.58 | 5600180.87
|  | Total Cash Inflows | 496912910.37 |  | 36524217.29 |  |  | 36524217.29
| Cash Outflows: | [6 empty] | 0
|  | Payment of Expenses | 70773304.31 |  | 2441617.41 | 4202385.27 | 2834830.73 | 9478833.41
|  | To Suppliers/Creditors | 158095249.02 |  | 93011.69 | 0 | 0 | 93011.69
|  | To Employees | 44696138.7 |  | 5653204.75 | 5833368.5 | 8052728.07 | 19539301.32
|  | Other Expenses | 99809729.85 |  | 4858458.61 | 9596221.49 | 8838815.92 | 23293496.02
|  | Total Cash Outflows | 373374421.88 |  | 13046292.46 |  |  | 13046292.46
| Net Cash from Operating Activities |  |  | 123538488.49 | 23477924.83 |  |  | 23477924.83
Cash Flows from Investing Activities | [7 empty] | 0
Cash Inflows:
|  | Total Cash Inflows | 0
| Cash Outflows: | [6 empty] | 0
|  | To Purchase Property, Plant & Equipment | 7011164.82 |  | -7748.76 | 2992640.21 | 7527131.44 | 10512022.89
|  | Total Cash Outflows | 7011164.82 |  | -7748.76 |  |  | -7748.76
| Net Cash from Investing Activities |  |  | -7011164.82 | #REF! |  |  | #REF!
0
Net Increase in Cash |  |  |  | 116527323.67 | #REF! |  |  | #REF!
Cash Beginning of the Period, January 1, 2022 |  |  |  | 1851886217 | 604430235.32 |  |  | 604430235.32
Cash at the End of the Period, June 30, 2022 |  |  |  | 1968413540.67 | 627915908.91
23485673.59
CERTIFIED CORRECT: |  |  | NOTED BY: |  | 116527323.67
FLORIDA S. CADANO |  |  | ENGR. ALBERT D. CHUA
City Accountant |  |  | City Mayor
116527323.67
0

## May
Republic of the Philippines
Province of Ilocos Norte
City Government of Batac
Report on Utilization of Disaster Risk Reduction and Management Fund | [6 empty] | january | february | march | april | may | june | july | august | september | october | november | december
As of May 31, 2022
Particulars | Quick Response Fund (QRF) 30% | Mitigation Fund (70%) | NDRRMF | From Other LGUs | From Other Sources | Total
A. Sources of Funds:
Currrent Appropriation | 12815451.88 | 29902721.05 |  |  |  | 42718172.93
Continuing Appropriation | [5 empty] | 35969476.1
2021 |  | 5406966
2020 |  | 7289525
2019 |  | 8553545
2018 |  | 2339826.94
2017 |  | 7614696.5
2016 |  | 4764916.66
Previous Year's Appropriations transferred to the Special Trust Fund | [5 empty] | 26702082.01
2019 |  | 11435457.97
2020 |  | 6683258.27
2021 |  | 8583365.77
Donations |  | 3000 |  |  |  | 3000 |  | -450000
Total Funds Available | 12815451.88 | 92577279.16 |  |  | 0 | 105392731.04
B. Utilization
Disaster Prevention and Mitigation
Clearing, pruning, brushing & cutting of trees in different barangays & schools |  | 102882.4 | [6 empty] | 43737.05 | 43543.15 | 15602.2
[9 empty] | 21514.85 | 25692.7 | 4753.3
[9 empty] | 7888 | 17850.45 | 5156
[9 empty] | 7555 |  | 5692.9
6779.2
Cash for work program before calamities |  | 0
Dredging, declogging, & cleaning of rivers, creeks, canals, small farm reservoirs & other waterways |  | 0
Disaster Preparedness
Conduct of capacity training of C/BDRRMC, SDRRMC, NGOs, Govt & private sectors & volunteers on DRRM |  | 0
Updating of various CDRRM plans |  | 0
Conduct of earthquake, flood & fire evacuation drills Oplan Ligtas Pamayanan |  | 0
Info Education Campaign; Early Warning Systems & Pre-evacuation Management, Disaster preparedness; production, |  | 0
formulation & distribution of materials (manuals, leaflets, pamphlets, flyers, brochures, posters, early warning
signages); dialogues with the school & community; and others
Conduct of DRRM Related Contest |  | 0
Stockpiling & Prepositionig of Supplies & Materials (Food & Nonfood items/medicines) |  | 971100 | [8 empty] | 971100
Acquisition of SRR eqpt. Personal protective gears & other facilities, materials, supplies and maintenance of evacuation |  | 0
center
Purchase of 1 unit Photocopying machine |  | 0
Purchase of 3 units computer printer |  | 0
Fogging and preventive measures against dengue |  | 0
Purchase of 1 unit brand new rescue vehicle |  | 0
Purchase of 2 units brand new Multi-purpose vehicle |  | 0
Purchase of 1 unit brand new Patient Transport vehicle |  | 0
Disaster Response, Rehabilitation and Recovery
Quick Response Fund | 859100 | [7 empty] | 149100 |  | 710000
215000
495000
Provision of basic needs of evacuees, responders & other staff on-duty (food, clothing, shelter, medicines & others) |  | 0
& other services
Fuel & oil for disaster response, relief operations, assessment of infras, agriculture, |  | 36149.8 | [6 empty] | 6847.9 | 3122.8 | 26179.1
fishery & livestock & other damages & other services
[9 empty] | 2431.2 |  | 11147.2
[9 empty] | 2603.2 |  | 15031.9
1813.5
Conduct of Nutrition in Emergencies Program |  | 0
Cash for work program every after calamities |  | 0
Infrastructure rehabilitaion- rehab/repair/maintenance of calamity & disaster damages |  | 0
Gravelling of road shoulders & backfilling potholes |  | 0
Stockpiling of gravel and sand for regravelling of roadshoulders and backfilling potholes |  | 0
Agricultural rehabilitation program for agriculture, fishery & livestock |  | 0
Emergency Shelter Assistance |  | 0
Repair & Maintenance of Vehicles, heavy equipt, machineries & other SRR equipments |  | 0
Total Utilization | 859100 | 1110132.2
Unutilized Balance | 11956351.88 | 91467146.96 |  |  |  | 103423498.84
Prepared by: | Certified Correct: |  |  | Approved by:
ARVIN FRANCIS N. LUMANG | FLORIDA S. CADANO |  |  | ENGR. ALBERT D. CHUA
CDRRMO | City Accountant |  |  | City Mayor