## Form 6-Trust Fund
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
REGION: | REGION I - ILOCOS REGION |  | CALENDAR YEAR: | 2023
PROVINCE: | ILOCOS NORTE |  | QUARTER: | 1
CITY/MUNICIPALITY: | CITY OF BATAC
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | Balance |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date |  | Previous Balance
Philhealth Capitation |  | 12906684.2 | 2011-2017 |  | 73.03% | 9426042.97 | 3480641.23 | 7649160.34 |  | ongoing | 3480641.23
Animal Bite Treatment Package |  | 1130000 | February 2017 |  | 99.5% | 1124557 | 5443 | 752657 |  | ongoing | 5443
TB-DOTS |  | 399975 | 2015-2017 |  | 68.48% | 273901 | 126074 | 273901 |  | ongoing | 126074
HCI Charges |  | 574675 | 2018-2019 |  | 0% | [5 empty] | 574675
Transfer for the Rehabilitation of Small Scale Irrigation Project | Brgy. Camandingan, Batac City, I.N. | 3000000 | June 13, 2014 delivery of materials |  | 100% | 2284116.5 |  | 2245966.5 |  | liquidated with refund of 715,883.50 Check # 638708 | 715883.5
Construction of Sumader SWIP | Brgy. Sumader, Batac City, I.N. | 29254500 |  |  | 63.09% | 29254500 | 0 |  |  | Second Billing paid under Voucher No. 100-2021-03-1161; Check No. 794803 | 0
Fund transfer for the conversion of existing Day Care Centers to Child Development Centers |  | 1000000 |  |  | 100% | 735206 | 264794 | 735206 |  | Fully liquidated, balance of P264,794.00 refunded under check no. 638775 | 264794
Technology Adoption & Commercialization of Hawaiian Ginger & Turmeric | Baligat, Camandingan, San Pedro | 2103093 | February 2017 |  | 100% | 1791754.88 | 853340.52 | 1782879.08 |  | Balance refunded under Voucher No. 100-2021-12-3856; Check No. 868222 | 311338.12
Rehabilitation of Baoa Diversion Dam | Baoa East, Baoa West | 1440000 | Receipt of Fund-July 2017 |  | 100% |  | 1440000 |  |  | with liquidating damages in the amount of P19,707.24 | 1440000
Establishment of Adolescent Friendly Health Facilities |  | 50000 | February 2018 |  | 100% | 50000 |  |  |  | liquidated | 0
Technology Adoption & Commercialization of Hawaiian Ginger & Turmeric | Baligat, Camandingan, San Pedro | 2103093 | Receipt of Fund December 2018 |  | 50% |  |  |  |  | Balance refunded under Voucher No. 100-2021-12-3856; Check No. 868222 | 2103093
Funding Support of Safe Closure and Rehabilitation Plan (SCRP) of Open and Controlled Dumpsite (Perimeter Fence) | Brgy. 31 Camandingan | 1822247.42 | Receipt of Fund December 2018 |  | 100% | 1822247.42 |  |  |  | First and Final Billing paid under Check No. 794602 in the amount of 1,822,247.42; with liquidation report | 0
Proposed Riverfront Promenade | Brgy. Ablan & Valdez | 7077100 | Receipt of Fund-March 2019 |  | 100% | 7042223.44 | 34876.56 |  |  | Liquidated: Final Billing paid under Voucher No. 100-2021-09-2728; Check No. 796089; Refund of 34,876.56 paid under Voucher No. 100-21-09-2806; Check No. 796091 | 34876.56
Riverfront Promenade Phase 2 | Brgy. Ablan & Valdez | 13750201 | Receipt of Fund-December 2019 |  | 88% | 4572740.74 |  |  |  | ongoing | 9177460.26
Performance Challenge Fund: |  | 3500000 | Receipt of Fund-December 2019 |  | 100% | 3490000 |  |  |  | Liquidated: First and Final Billing paid under Voucher No. 300-21-07-018; Check No. 688007; Refund of 10,000 paid under Voucher No. 300-2021-07-19; Check No. 688008 | 10000
Share of the City-2012 7171 Excise Tax- | [10 empty] | 0
Construction/Rehabilitation of Farm to Market Road | 22 rural barangays | 34500000 | October,2015 |  | 100% | 34167234.31 | 332765.69 | 34167234.31 |  | completed | 332765.69
Share of the City-Direct shares of Congressional Districts for the 2012 Excise Tax: | [10 empty] | 0
Farm to Market Road | rural barangays | 15000000 | November,2015 |  | 100% | 14280464.15 | 719535.85 | 14280464.15 |  | completed | 719535.85
Purchase of Various Equipment | 43 barangays | 40745187 | November,2015 |  | 92.15% | 37546995 | 12597192 | 37546995 |  | ongoing | 3198192
Buy -back and Other Marketing | [10 empty] | 0
Programs for Critical Alternative crops to tobacco |  | 4000000 | November,2015 |  | 89.55% | 3581998.24 | 418001.76 | 3581998.24 |  | ongoing | 418001.76
Local Government Support Fund: | [10 empty] | 0
SALINTUBIG(Sagana at Ligtas na Tubig sa Lahat) Provision of Portable Water Supply | [9 empty] | For Final Billing | 0
| Pimentel | 500000 | 2017-10-22 |  | 100% | [5 empty] | 500000
| Maipalig | 1060000 | 2017-10-22 |  | 100% | [5 empty] | 1060000
0
FY 2020 Local Government Support Fund-Assistance to Cities (Riverfront Promenade 3) |  | 10647492 | Receipt of Fund- November 2021 | [6 empty] | Notice to Proceed already issued to the Contractor. | 10647492
Local Government Support Fund- Financial Assistance to LGUs (Procurement of Rescue Kit) |  | 2500000 | Receipt of Fund -December 2022 | [6 empty] | Procurement Process Ongoing | 2500000
DSWD-RF01 | [10 empty] | 0
Cost for Viand and Rice for 1,050 Children in the implementation of SFP CY 2017 |  | 1890000 | Receipt of Fund-September 2018 |  | 50.21% | 948991.96 | 1890000 |  |  | Fully Liquidated, with a refund of 941,008.04; Check No. 638772 | 941008.04
Fund Transfer-Social Pension 3rd Qtr |  | 1264500 | Receipt of Fund-October 2018 |  | 100% | 1264500 | 0 | 1264500 |  | liquidated | 0
Fund Transfer-Social Pension 4th Qtr |  | 1264500 | Receipt of Fund-October 2018 |  | 100% | 1264500 | 0 | 1264500 |  | liquidated | 0
ATI-RTC I | [10 empty] | 0
Funding Support for the Sustainable Community Development Through the Conduct of Series of Training Under the Extension Program fro Agri-Fisheries and National Development (Expand) or Grant System |  | 905000 | Receipt of Fund-December 27, 2018 |  | 100% | 876294.28 | 28705.72 | 111357.38 |  | liquidated with refund of 28,705.71 Check # 638717 | 28705.72
DEPARTMENT OF ENERGY | [10 empty] | 0
ER 1-94 COVID related projects of the City Government of Batac (from the DOE) | City of Batac, Ilocos Norte | 200000 | August 2020 |  | 100% | 193836 |  |  |  | According to DOE, the balance of P6,164 will be used to purchase alcohol. | 6164
DANGEROUS DRUGS BOARD | [10 empty] | 0
Financial Assistance-Dangerous Drugs Board |  | 6000000 | Receipt of Fund- December 2021 |  | 0% | 0 |  |  |  | Project Ongoing | 6000000 | (Reference: Consolidated Quarterly Report on Government Projects/Programs/Activities For the First Quarter, CY 2023)
OFFICE OF THE PRESIDENT | [10 empty] | 0
Financial Assistance to cater and address the immediate needs of the people affected by the health crisis brought about by the Corona Virus Disease (COVID-19) per approved Memorandum dated March 4, 2021 | City of Batac, Ilocos Norte | 5000000 | Receipt of Fund March 2021 |  | 100% | 4963262 |  |  |  | Liquidated with refund to Office of the President amounting to P36,738.00 under Check No. 638811 | 36738
Financial assistance of people affected by Covid-19 | City of Batac, Ilocos Norte | 10000000 | July 2022 |  | 0% | 0 |  |  |  | Refunded to OP-Socio Civic Projects Fund under Check No. 638814
DEPARTMENT OF HEALTH-CENTER FOR HEALTH DEVT. I
One Covid-19 Allowance (OCA)- for the month of January 2022 |  | 732125 | Receipt of Fund- July 25, 2022 |  | 98.77% | 723125 |  |  |  | Liquidated; Balance of 9,000 refunded under Check No. 638818 dated August 17, 2022
One Covid-19 Allowance (OCA)- for the month of February 2022 |  | 799125 | Receipt of Fund- July 25, 2022 |  | 100% | 799125 |  |  |  | Liquidated
Meals, accomodation & transportation benegits as per Admin Order #2021-0062 for the period Sept 15 to Dec 19, 2020 |  | 210000 | Receipt of Fund- July 25, 2022 |  | 96.67% | 203000 |  |  |  | Liquidated. Balance of 7,000 refunded under Check No. 638818 dated August 17, 2022
One Covid Allowance for the month of April 2022 |  | 709625 |  |  | 100% | 709625 |  |  |  | Liquidated | 0
One Covid Allowance for the month of June 2022 |  | 650625 |  |  | 100% | 650625 |  |  |  | Liquidated | 0
Generics Awareness Month |  | 46600 | Receipt of Fund- October 2022 |  | 31.15% | 14517.4 |  |  |  |  | 32082.6
Health Emergency Allowance (HEA) for the month of May, July, August and September 2022. |  | 2075312.5 | Receipt of Fund- February 2023 |  | 100% | 2075312.5 |  |  |  | completed | 0
DSWD-RO I | [10 empty] | 0
Rehabilitation of Senior Citizen Building | [9 empty] | liquidating damages in the amount of P20,809.15 | 0
DEPARTMENT OF LABOR AND EMPLOYMENT RO1 | [10 empty] | 0
DOLE Regional Office 1 (Provision of various Processing Equpment for Peanut Processing (Self-Employed with insuficient income) |  | 758152 | Receipt of Fund- October 2022 |  | 0% | 0 |  |  |  | Notice to Proceed already issued to the Supplier | 758152
DEPARTMENT OF AGRICULTURE RFO1 | [10 empty] | 0
Rehabilitation/Improvement of various small- scale irrigation projects (SSOPC) in City of Batac, Ilocos Norte |  | 26500000 | Receipt of Fund- March 2023 |  | 0% | . |  |  |  |  | 0
Others: | [10 empty] | 0
C and G Environmental Management Corporation |  | 121000 | Receipt of Fund- September 2022 |  | 0% | [5 empty] | 121000
Commission on Population & Development (Social Protection for Adolescent Mothers and their Children) |  | 200000 | Receipt of Fund- September 2022 |  | 52.5% | 105000 |  |  |  |  | 95000
911 Library - The Delivery of Supplementary Reference and Research Materials through an Accessible Community Satellite Library for Modular Learning of the Learners of the Three Barangays (Bungon, Baay and Billoca) | Brgy. Bungon, Baay and Billoca | 270000 | Receipt of Fund-August 31, 2022 |  | 100% | 270000 |  |  |  | Liquidated | 0
PBSP-CHO PMDT |  | 7610 | December 2017 |  | 0% | 0 |  |  |  |  | 7610
Sustainable Development Goals-Family Based Actions for Children and their Environment in the Slims (SDG FACES) |  | 50000 | November 2017 |  | 0% | 0 |  |  |  | not implemented | 50000
Cash Donation Support to PNCR-Ilocos Norte Chapter |  | 3000 | March 2017 |  | 0% | 0 |  |  |  |  | 3000 | 9. Commission on Polpulation & Development (Social Protection for Adolescent Mothers and their Children)
Prizes for Most Outstanding Farmers |  | 100000 | January 2017 |  | 0% | 0 |  |  |  |  | 100000 | 8. C and G Environmental Management Corporation
Travelling Allowance for existing BNS for 2019 |  | 56400 | Receipt of Fund-June 2019 |  | 100% | 56400 |  |  |  | completed | 0
SOCIAL AMELIORATION PROGRAM | City of Batac, Ilocos Norte | 51700000 | April 2020 |  | 100% | 51700000 |  |  |  | Fully liquidated | 0
SOCIAL PENSION for Indigent Senior Citizen for the 1st Semester of 2020 | City of Batac, Ilocos Norte | 2319000 | June 2020 |  | 100% | 2319000 |  |  |  | Fully Liquidated, with a refund of 114,000; Check No. 638768 | 0
Provision of Water Pumps (Department of Labor and Employment) | City of Batac, Ilocos Norte | 1400000 | July 2020 |  | 100% | 1399950 |  |  |  | Voucher and check of refund in the amount of P50.00 was prepared under V#300-2021-03-009; check#638783 | 50
Travelling Allowance for existing BNS for 2022 |  | 55200 | Receipt of Fund-May 23, 2022 |  | 0% | 55200 |  |  |  |  | 0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
WILMA T. ICUSPIT |  |  | FLORIDA S. CADANO |  |  | ENGR. ALBERT D. CHUA
Local Budget Officer |  |  | Local Accountant |  |  | Local Chief Executive

## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: |  |  | CALENDAR YEAR: | 2023
PROVINCE: |  |  | QUARTER: | 1
CITY/MUNICIPALITY:
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development
Support to COVID-19 related PPAs | All Barangays | 1157843.8 | 2023-01-01 | 2023-12-31 | - | -
Economic Development (pls list down specific projects)
Purchase of Tail Lift (1 ton capacity) | Slaughterhouse | 150000 | 2023-01-01 | 2023-12-31 | - | -
Purchase of Fertilizer for distribution to Farmers | Rural Barangays | 80000000 | 2023-01-01 | 2023-12-31 | - | - |  | Procurement on Going
Purchase of Palay Seeds for Distribution to Farmers | Rural Barangays | 20000000 | 2023-01-01 | 2023-12-31 | - | - |  | Procurement on Going
Purchase of Assorted Hybrid Vegetables Seeds for Distribution to Farmers | Rural Barangays | 2000000 | 2023-01-01 | 2023-12-31 | - | - |  | Procurement on Going
Purchase & Installation of Public Address System for the whole public market with complete accessories | Public Market | 500000 | 2023-01-01 | 2023-12-31 | - | -
Acquisition of 1 unit Digital Weighing Scale for Hogs and Large Animals | Slaughterhouse | 1000000 | 2023-01-01 | 2023-12-31 | - | -
Purchase of Weighing Scale for Distribution to Barangay | All Barangays | 1000000 | 2023-01-01 | 2023-12-31 | - | -
Environmental Management
Solid Waste management Implementation
Purchase of 2 units Garbage Compactor |  | 5000000
Purchase of 2 units Dump Truck |  | 10000000
Purchase of 2 units Forward Truck (Drop-side) |  | 6000000
Grand Total |  | 126807843.8
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
| WILMA T. ICUSPIT |  |  |  | ENGR. ALBERT D. CHUA
| Local Budget Officer |  |  |  | Local Chief Executive

## Form 8 LDRRMFU
FDP Form 8 - Local Disaster Risk Reduction and Management Fund Utilization
(Commission on Audit Form)
LOCAL DISASTER RISK REDUCTION AND MANAGEMENT FUND UTILIZATION
REGION: | REGION I - ILOCOS REGION |  | CALENDAR YEAR: | 2023
PROVINCE: | ILOCOS NORTE |  | QUARTER: | 1
CITY/MUNICIPALITY: | CITY OF BATAC
Particulars | LDRRM Fund |  | NDRRM Fund | From Other LGUs | From Other Sources | Total
| Quick Response Fund (QRF) 30% | Mitigation Fund 70%
A. Sources of Funds:
Currrent Appropriation | 11311184.72 | 26392764.36 |  |  |  | 37703949.08
Continuing Appropriation | [5 empty] | 49222130.1
2022 |  | 13260620
2021 |  | 5400000
2020 |  | 7288525
2019 |  | 8553545
2018 |  | 2339826.94
2017 |  | 7614696.5
2016 |  | 4764916.66
Previous Year's Appropriations transferred to the Special Trust Fund | [5 empty] | 48494931.49
2019 |  | 11435457.97
2020 |  | 6683258.27
2021 |  | 8583365.77
2022 |  | 21792849.48
Donations |  | 3000 |  |  |  | 3000
Total Funds Available | 11311184.72 | 124112825.95 |  |  | 0 | 135424010.67
B. Utilization
Disaster Prevention and Mitigation
Clearing, pruning, brushing & cutting of trees in different barangays & schools |  | 30674.7 | [5 empty] | 10766 |  | 19908.7
[7 empty] | 02-299 | 5508.7 | 03-040 | 8667.4
[7 empty] | 02-300 | 5257.3 | 03-315 | 5424.4
[9 empty] | 03-531 | 5816.9
Cash for work program before calamities |  | 0
Dredging, declogging, & cleaning of rivers, creeks, canals, small farm reservoirs & other waterways |  | 0
Disaster Preparedness
Conduct of capacity training of C/BDRRMC, SDRRMC, NGOs, Govt & private sectors & volunteers on DRRM |  | 9500 | [7 empty] | 9500
[9 empty] | 03-316 | 9500
Updating of various CDRRM plans |  | 0
Conduct of earthquake, flood & fire evacuation drills Oplan Ligtas Pamayanan |  | 0
Info Education Campaign; Early Warning Systems & Pre-evacuation Management, Disaster preparedness; production, |  | 0
formulation & distribution of materials (manuals, leaflets, pamphlets, flyers, brochures, posters, early warning
signages); dialogues with the school & community; and others
Conduct of DRRM Related Contest |  | 68000 | [7 empty] | 68000
[9 empty] | 03-414 | 68000
Stockpiling & Prepositionig of Supplies & Materials (Food & Nonfood items/medicines) |  | 0
Acquisition of SRR eqpt. Personal protective gears & other facilities, materials, supplies and maintenance of evacuation center |  | 0
Purchase of 1 unit Laptop Computer |  | 0
Purchase of 1 unit Dekstop Computer |  | 0
Purchase of 1 set Multi-hazard Early Warning Device |  | 0
Purchase of 2 sets CPR Mannequin |  | 0
Purchase of 1 set Air-lifting Flat Bags |  | 0
Purchase of 1 set Vehicle Stabilization Kit |  | 0
Disaster Response, Rehabilitation and Recovery
Quick Response Fund | 0
Provision of basic needs of evacuees, responders & other staff on-duty (food, clothing, shelter, medicines & others) |  | 0
& other services
Cash for work program every after calamities |  | 0
Infrastructure rehabilitaion- rehab/repair/maintenance of calamity & disaster damages |  | 0
Gravelling of road shoulders & backfilling potholes |  | 0
Stockpiling of gravel and sand for regravelling of roadshoulders and backfilling potholes |  | 0
Agricultural rehabilitation program for Agriculture, Fishery & Livestock |  | 0
Emergency Shelter Assistance |  | 0
Total Utilization | 0 | 108174.7
Unutilized Balance | 11311184.72 | 124004651.25 |  |  |  | 135315835.97
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
FLORIDA S. CADANO
Local Accountant

## Form 13 - MANCOM
FDP Form 13 - Manpower Complement
HUMAN RESOURCE COMPLEMENT
REGION: | REGION I - ILOCOS REGION | CALENDAR YEAR: | 2023
PROVINCE: | ILOCOS NORTE | QUARTER: | 1
CITY/MUNICIPALITY: | CITY OF BATAC
Nature of Appointment or Employment | Number | Compensation and Other Benefits |  | Total
|  | Salaries and Wages | Other Monetary Benefits
I. Permanent | 254 | 19349182.73 | 7853779.21 | 27202961.94
II. Contractual |  |  |  | 0
III. Job Order/Contract of Service | 190 | 5324085.72 |  | 5324085.72
IV. Casual | 71 | 2032594.45 | 1171949.34 | 3204543.79
Grand Total | 515 | 26705862.9 | 9025728.55 | 35731591.45
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
MARLON F. SORIA |  | FLORIDA S. CADANO | ENGR. ALBERT D. CHUA
Human Resource Management Officer |  | Local Accountant | Local Chief Executive
Notes:
1. Contractual personnel are those whose employment in the government is in accordance with a special contract to undertake a specific work or job, requiring special or technical skills not available in the employing agency, to be accomplished within a specific period, which in no case shall exceed one year, and performs or accomplishes the specific work or job, under his own responsibility with a minimum of direction and supervision from the hiring agency. (Source: Presidential Decress No. 807 October 6, 1975) 2.Contract of Services/Job Orders are employees whose services rendered are not considered government services and do not enjoy the benefits enjoyed by government employees. The job order covers piece work or intermittent job of short duration not exceeding six months on a daily basis. (Source: Omnibus Rules Implementing Book V of E.O. No. 292 and Other Pertinent Civil Service Laws)

## Form 12 - UCA
FDP Form 12 - Unliquidated Cash Advances
UNLIQUIDATED CASH ADVANCES
REGION: | REGION I - ILOCOS REGION |  | CALENDAR YEAR: | 2023
PROVINCE: | ILOCOS NORTE |  | QUARTER: | 1
CITY/MUNICIPALITY: | CITY OF BATAC
Name of Debtor (in alphabetical order) | Amount Balance | Date Granted | Purpose | Amount Due
|  |  |  | Current |  |  | Past Due
|  |  |  | Less than 30 days | 31-90 days | 91-365 days | Over 1 year | Over 2 years | 3 years and above
Kerwin Angelo N. Saguiguit | 7540 | 2023-03-13 | Registration Fee & Per Diem | 7540
Richard A. Pungtilan | 7540 | 2023-03-13 | Registration Fee & Per Diem | 7540
Tristan Melecia D. Advincula | 12350 | 2023-03-17 | Registration Fee & Per Diem | 12350
Ferdinand B. Casil, Jr. | 12350 | 2023-03-17 | Registration Fee & Per Diem | 12350
Noralyn I. Manahan | 12350 | 2023-03-17 | Registration Fee & Per Diem | 12350
Celeste G. Abundo | 12350 | 2023-03-17 | Registration Fee & Per Diem | 12350
Robert Joe Y. Pagtama | 12350 | 2023-03-17 | Registration Fee & Per Diem | 12350
Roger B. Saguiguit | 7500 | 2023-03-17 | Fuel, Oil & Lubs & Per Diem | 7500
Lovely Gay N. Alibuyog | 9440 | 2023-03-23 | Registration Fee, Transportation & Per Diem | 9440
Gene T. Gonzales | 12650 | 2023-03-24 | Registration Fee & Per Diem | 12650
Charlie M. Abitong | 12650 | 2023-03-24 | Registration Fee & Per Diem | 12650
Ariel R. Austria | 17250 | 2023-03-24 | Fuel, Oil & Lubs, Toll & Per Diem | 17250
Vanny C. Gamet | 12650 | 2023-03-24 | Registration Fee & Per Diem | 12650
Toribio A. Melad, Jr. | 5500 | 2023-03-24 | Per Diem | 5500
Robert John M. Ignacio | 5500 | 2023-03-24 | Per Diem | 5500
Maria Bernadeth R. Salamitao | 900 | 2023-03-27 | Per Diem | 900
Regie M. Viernes | 900 | 2023-03-27 | Per Diem | 900
Jay D. Ulit | 5250 | 2023-03-27 | Per Diem | 5250
Rojanie Joy J. Sacubo | 389300 | 2023-03-27 | Cash for Work Every After Calamities | 389300
Total | 556320 |  |  | 556320
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
FLORIDA S. CADANO |  |  | ENGR. ALBLERT D. CHUA
Local Accountant |  |  | Local Chief Executive

## FDP FORM 10a
FDP Form 10a - Bid Results on Civil Works
Note: Bid Results are in three (3) separate forms, particularly, for Civil Works (Form 10a -CW), Goods and Services (Form 10b - GS) and Consulting Services
(Form 10c - CS). If there is no bidded project, good or service for the quarter, the forms must still be submitted with the said notation and signed accordingly.
CIVIL WORKS BID-OUT
REGION: | REGION I - ILOCOS REGION |  | CALENDAR YEAR: | 2023
PROVINCE: | ILOCOS NORTE |  | QUARTER: | 1
CITY/MUNICIPALITY: | CITY OF BATAC
No. | Reference No. | Name of Project | Approved Budget for Contract | Location | Winning Bidder | Name and Address | Bid Amount | Bidding Date | Contract Duration
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
| BAC Secretariat Head |  |  |  | BAC Chairperson

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2

## FDP FORM 10b
FDP Form 10b - Bid Results on Goods and Services
Note: Bid Results are in three (3) separate forms, particularly, for Civil Works (Form 10a -CW), Goods and Services (Form 10b - GS) and Consulting Services
(Form 10c - CS). If there is no bidded project, good or service for the quarter, the forms must still be submitted with the said notation and signed accordingly.
GOODS AND SERVICES BID-OUT
REGION: | REGION I - ILOCOS REGION |  | CALENDAR YEAR: | 2023
PROVINCE: | ILOCOS NORTE |  | QUARTER: | 1
CITY/MUNICIPALITY: | CITY OF BATAC
Reference No. | Item Description | Approved Budget for Contract | Winning Bidder | Name and Address Of Bidder | Bid Amount | Date of Bidding
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
| BAC Secretariat Head |  |  | BAC Chairperson

## FDP FORM10c
FDP Form 10c - Bid Results on Consulting Services
Note: Bid Results are in three (3) separate forms, particularly, for Civil Works (Form 10a -CW), Goods and Services (Form 10b - GS) and Consulting Services
(Form 10c - CS). If there is no bidded project, good or service for the quarter, the forms must still be submitted with the said notation and signed accordingly.
CONSULTING SERVICES BID-OUT
REGION: | REGION I - ILOCOS REGION |  | CALENDAR YEAR: | 2023
PROVINCE: | ILOCOS NORTE |  | QUARTER: | 1
CITY/MUNICIPALITY: | CITY OF BATAC
No. | Reference No. | Name of Project | Location | Approved Budget for Contract | Winning Bidder | Name and Address | Bid Amount | Bidding Date | Contract Duration
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
| BAC Secretariat Head |  |  |  | BAC Chairperson

## Form 8 - LDRRMFU
FDP Form 8 - Local Disaster Risk Reduction and Management Fund Utilization
(Commission on Audit Form)
LOCAL DISASTER RISK REDUCTION AND MANAGEMENT FUND UTILIZATION
REGION: | REGION I - ILOCOS REGION |  | CALENDAR YEAR: | 2023
PROVINCE: | ILOCOS NORTE |  | QUARTER: | 1
CITY/MUNICIPALITY: | CITY OF BATAC
Particulars | LDRRM Fund |  | NDRRM Fund | From Other LGUs | From Other Sources | Total
| Quick Response Fund (QRF) 30% | Mitigation Fund 70%
A. Sources of Funds
Current Appropriations
Continuing Appropriations
Previous Years' Appropriations Transferred to the Special Trust Fund
(Year 1)
(Year 2)
(Year 3)
(Year 4)
(Year 5)
Transfer/Grants
Total Funds Available
B. Utilization
Medicines
Food Supplies
Repair of Evacuation Center
Trainings
Construction of Evacuation Center
Equipment
Transfers to other LGUs
Total Utilization
Unutilized Balance
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
Local Accountant