## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | I | CALENDAR YEAR: | 2023 | [13 empty] | 2023
PROVINCE: | ILOCOS NORTE | QUARTER: | 2 | [13 empty] | SECOND
CITY/MUNICIPALITY: | BATAC
FUNCTION/PROGRAM PROJECT ACTIVITY |  |  | LOCATION/COVERAGE | TOTAL COST | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | NO. OF EXTENSIONS, IF ANY | REMARKS
[19 empty] | % OF COMPLETION | TOTAL COST INCURRED
SOCIAL DEVELOPMENT
| Support to COVID-19 related PPAs |  | All Barangays | 1157843.8 | [13 empty] | Jan.-Dec. 2023 | 0% | 0
| Sub-total |  |  | 1157843.8 | [15 empty] | 0
ECONOMIC DEVELOPMENT
| Purchase of Tail Lift (1 ton capacity) |  | Slaughterhouse | 150000 | [13 empty] | Jan.-Dec. 2023 | 0% | 0
| Purchase of Fertilizer for distribution to Farmers |  | Rural Barangays | 80000000 | [13 empty] | Jan.-Dec. 2023 | 79.19% | 63348825 |  | Procurement on going
| Purchase of Palay Seeds for Distribution to Farmers |  | Rural Barangays | 20000000 | [13 empty] | Jan.-Dec. 2023 | 25.63% | 5126000 |  | Procurement on going
| Purchase of Assorted Hybrid Vegetables Seeds for Distribution to Farmers |  | Rural Barangays | 2000000 | [13 empty] | Jan.-Dec. 2023 | 0% | 0 |  | Procurement on going
| Purchase & Installation of Public Address System for the whole public market with complete accessories |  | Public Market | 500000 | [13 empty] | Jan.-Dec. 2023 | 0% | 0
| Acquisition of 1 unit Digital Weighing Scale for Hogs and Large Animals |  | Slaughterhouse | 1000000 | [13 empty] | Jan.-Dec. 2023 | 0% | 0
| Purchase of Weighing Scale for Distribution to Barangay |  | All Barangays | 1000000 | [13 empty] | Jan.-Dec. 2023 | 0% | 0 |  | Procurement on going
| Sub-total |  |  | 104650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0482 | 68474825
ENVIRONMENTAL MANAGEMENT
Solid Waste management Implementation
| Purchase of 2 units Garbage Compactor |  |  | 5000000 | [13 empty] | Jan.-Dec. 2023 | 0% | 0 |  | Procurement on going
| Purchase of 2 units Dump Truck |  |  | 10000000 | [13 empty] | Jan.-Dec. 2023 | 0% | 0 |  | Procurement on going
| Purchase of 2 units Forward Truck (Drop-side) |  |  | 6000000 | [13 empty] | Jan.-Dec. 2023 | 0% | 0 |  | Procurement on going
| Sub-total |  |  | 21000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | 0
| TOTAL SPA-20% DF |  |  | 126807843.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 54% | 68474825
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
| WILMA T. ICUSPIT | ENGR. ALBERT D. CHUA
| City Budget Officer | City Mayor

## FORM 12
FDP Form 12 - Unliquidated Cash Advances
UNLIQUIDATED CASH ADVANCES
REGION: REGION I |  |  | CALENDAR YEAR: | 2023
PROVINCE: ILOCOS NORTE |  |  | QUARTER: | 2
CITY/MUNICIPALITY: CITY GOVERNMENT OF BATAC
Name of Debtor (in alphabetical order) | Amount Balance | Date Granted | Purpose | Amount Due
|  |  |  | Current |  |  | Past Due
|  |  |  | Less than 30 days | 31-90 days | 91-365 days | Over 1 year | Over 2 years | 3 years and above
Anne Bernadeth C. Samsam | 2650 | 2023-06-19 | Travel | 2650
Ariel R. Austria | 8250 | 2023-06-26 | Travel | 8250
Christopher B. Lagmay | 23400 | 2023-06-19 | Travel | 23400
Joselle Mariya C. Arcibal | 10800 | 2023-06-21 | Travel | 10800
Kathleen Joy C. Acosta | 1000 | 2023-06-15 | Travel | 1000
Kylie B. Diao | 16000 | 2023-06-20 | Registration Fee | 16000
Lucky Rene G. Bunye | 23400 | 2023-06-19 | Travel | 23400
Rose Marie A. Oallesma | 10800 | 2023-06-21 | Travel | 10800
Sherryl Mae V. Ulit | 10800 | 2023-06-21 | Travel | 10800
Vanny C. Gamet | 8000 | 2023-06-22 | Registration Fee | 8000
Total | 115100 |  |  | 115100
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
SGD
JOSELLE MARIYA C. ARCIBAL |  |  | ENGR. ALBERT D. CHUA
Acting City Accountant |  |  | Local Chief Executive

## FORM 13
FDP Form 13 - Manpower Complement
HUMAN RESOURCE COMPLEMENT
REGION: REGION I |  | CALENDAR YEAR: | 2023
PROVINCE: ILOCOS NORTE |  | QUARTER: | 2
CITY/MUNICIPALITY: CITY GOVERNMENT OF BATAC
Nature of Appointment or Employment | Number | Compensation and Other Benefits |  | Total
|  | Salaries and Wages | Other Monetary Benefits
I. Permanent | 251 | 40661262.56 | 23661973.68 | 64323236.24
II. Contractual
III. Job Order/Contract of Service | 196 | 12332239.79 |  | 12332239.79
IV. Casual | 71 | 4446888.49 | 3039836.55 | 7486725.04
Grand Total | 518 | 57440390.84 | 26701810.23 | 84142201.07 | 71809961.28
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
SGD
MARLON F. SORIA |  | JOSELLE MARIYA C. ARCIBAL |  | ENGR. ALBERT D. CHUA
Human Resource Management Officer |  | Acting City Accountant |  | Local Chief Executive
Notes:
1. Contractual personnel are those whose employment in the government is in accordance with a special contract to undertake a specific work or job, requiring special or technical skills not available in the employing agency, to be accomplished within a specific period, which in no case shall exceed one year, and performs or accomplishes the specific work or job, under his own responsibility with a minimum of direction and supervision from the hiring agency. (Source: Presidential Decress No. 807 October 6, 1975) 2.Contract of Services/Job Orders are employees whose services rendered are not considered government services and do not enjoy the benefits enjoyed by government employees. The job order covers piece work or intermittent job of short duration not exceeding six months on a daily basis. (Source: Omnibus Rules Implementing Book V of E.O. No. 292 and Other Pertinent Civil Service Laws)

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2
43