## IRA UTILIZATION 4TH QTR 2022
20% COMPONENT OF THE IRA UTILIZATION
FOR THE FOURTH QUARTER CY 2022
CURRENT LEGISLATIVE APPROPRIATION
FUNCTION/PROGRAM PROJECT ACTIVITY |  |  | LOCATION/ COVERAGE | TOTAL COST | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | NO. OF EXTENSIONS, IF ANY | REMARKS
[19 empty] | % OF COMPLETION | TOTAL COST INCURRED
SOCIAL DEVELOPMENT
| Recovery Assistance to Hog Raisers affected to African Swine Fever (ASF) |  | All Barangays | 10000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Support to COVID-19 related PPAs |  | All Barangays | 20000000 | [13 empty] | Jan.-Dec. 2022 | 4.511% | 902165
| Sub-total |  |  | 30000000 | [15 empty] | 902165
ECONOMIC DEVELOPMENT
| Concreting of Farm-to-Market Road |  | Various Barangays | 40261034.8 | [13 empty] | Jan.-Dec. 2022 | 0% | 0 |  | Under Procurement
| Road Widening |  | Various Barangays | 500000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Additional Funding for the Construction of Sumader SWIP |  | Brgy. Sumader | 20000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Rehabilitation of Spillway |  | Various Barangays | 2000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Concreting of irrigation Canal |  | Various Barangays | 5000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Rehabilitation /Excavation of Small Farm Reservior (SFR) |  | Various Barangays | 2000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Construction and rehabilitation of Diversion Dam |  | Various Barangays | 5000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Development of Public Market | [16 empty] | Jan.-Dec. 2022 |  | 0
| Installation of Cargo Lift (3 units) |  | Public Market | 5000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Installation of Elecrical Wirings for Bldg. 1-6 |  | Public Market | 3000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Sub-total |  |  | 82761034.8 | [15 empty] | 0
ENVIRONMENTAL MANAGEMENT
Solid Waste management Program
| Upkeeping & preservation of the City Waste Disposal Site |  | City Dumpsite | 500000 | [13 empty] | Jan.-Dec. 2022 | 95.85% | 479240.66
| Construction of Slope Protection & Drainage System along the Garbage pond & Concreting of Road Network |  | Various Barangays | 8000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Purchase of Dumptruck |  | n/a | 5000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Construction of Roadway Slope Protection |  | Various Barangays | 20000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Dredging of Waterways (rivers/ creeks/ canals) |  | Various Barangays | 2000000 | [13 empty] | Jan.-Dec. 2022 | 0% | 0
| Sub-total |  |  | 35500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1.35% | 479240.66
| TOTAL SPA-20% DF |  |  | 148261034.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 6.284e-09% | 0.9317%
Supplemental Budget No. 3-Reversion- (20% Development Fund-CY 2015-2021)
SOCIAL DEVELOPMENT
| Construction of Covered Court at Barangay Quiom |  | Various Barangays | 4000000 | [13 empty] | Dec. 2022 | 0% | 0
| Sub-Total |  |  | 4000000
ECONOMIC DEVELOPMENT
| Purchase of Fertilizer for Distribution to Farmers |  | Various Barangays | 10000000 | [13 empty] | Dec. 2022 | 99.85% | 9985115
| Purchase of 4 Units Backhoe |  | n/a | 16000000 | [13 empty] | Dec. 2022 | 0% | 0 |  | Under Procurement
| Sub-total |  |  | 26000000 | [14 empty] | 38.4% | 9985115
| TOTAL SPA-20% DF |  |  | 30000000 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 33.28% | 9985115
GRAND TOTAL |  |  |  | 178261034.8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 6.376% | 11366520.66
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
|  | WILMA T. ICUSPIT | [16 empty] | ENGR. ALBERT D. CHUA
|  | City Budget Officer | [16 empty] | City Mayor

## TRUST FUND UTILIZATION 4TH QTR
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 4th QUARTER, CY 2022
Province, City or Municipality: BATAC CITY
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | Balance |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date |  | Previous Balance
Philhealth Capitation |  | 12906684.2 | 2011-2017 |  | 73.03% | 9426042.97 | 3480641.23 | 7649160.34 |  | ongoing | 3480641.23
Animal Bite Treatment Package |  | 1130000 | February 2017 |  | 99.5% | 1124557 | 5443 | 752657 |  | ongoing | 5443
TB-DOTS |  | 399975 | 2015-2017 |  | 68.48% | 273901 | 126074 | 273901 |  | ongoing | 126074
HCI Charges |  | 574675 | 2018-2019 |  | 0% | [5 empty] | 574675
Transfer for the Rehabilitation of Small Scale Irrigation Project | Brgy. Camandingan, Batac City, I.N. | 3000000 | June 13, 2014 delivery of materials |  | 100% | 2284116.5 |  | 2245966.5 |  | liquidated with refund of 715,883.50 Check # 638708 | 715883.5
Construction of Sumader SWIP | Brgy. Sumader, Batac City, I.N. | 29254500 |  |  | 63.09% | 29254500 | 0 |  |  | Second Billing paid under Voucher No. 100-2021-03-1161; Check No. 794803 | 0
Fund transfer for the conversion of existing Day Care Centers to Child Development Centers |  | 1000000 |  |  | 100% | 735206 | 264794 | 735206 |  | Fully liquidated, balance of P264,794.00 refunded under check no. 638775 | 264794
Technology Adoption & Commercialization of Hawaiian Ginger & Turmeric | Baligat, Camandingan, San Pedro | 2103093 | February 2017 |  | 100% | 1791754.88 | 853340.52 | 1782879.08 |  | Balance refunded under Voucher No. 100-2021-12-3856; Check No. 868222 | 311338.12
Rehabilitation of Baoa Diversion Dam | Baoa East, Baoa West | 1440000 | Receipt of Fund-July 2017 |  | 100% |  | 1440000 |  |  | with liquidating damages in the amount of P19,707.24 | 1440000
Establishment of Adolescent Friendly Health Facilities |  | 50000 | February 2018 |  | 100% | 50000 |  |  |  | liquidated | 0
Technology Adoption & Commercialization of Hawaiian Ginger & Turmeric | Baligat, Camandingan, San Pedro | 2103093 | Receipt of Fund December 2018 |  | 50% |  |  |  |  | Balance refunded under Voucher No. 100-2021-12-3856; Check No. 868222 | 2103093
Funding Support of Safe Closure and Rehabilitation Plan (SCRP) of Open and Controlled Dumpsite (Perimeter Fence) | Brgy. 31 Camandingan | 1822247.42 | Receipt of Fund December 2018 |  | 100% | 1822247.42 |  |  |  | First and Final Billing paid under Check No. 794602 in the amount of 1,822,247.42; with liquidation report | 0
Proposed Riverfront Promenade | Brgy. Ablan & Valdez | 7077100 | Receipt of Fund-March 2019 |  | 100% | 7042223.44 | 34876.56 |  |  | Liquidated: Final Billing paid under Voucher No. 100-2021-09-2728; Check No. 796089; Refund of 34,876.56 paid under Voucher No. 100-21-09-2806; Check No. 796091 | 34876.56
Riverfront Promenade Phase 2 | Brgy. Ablan & Valdez | 13750201 | Receipt of Fund-December 2019 |  | 82% | 4572740.74 |  |  |  | ongoing | 9177460.26
Performance Challenge Fund: |  | 3500000 | Receipt of Fund-December 2019 |  | 100% | 3490000 |  |  |  | Liquidated: First and Final Billing paid under Voucher No. 300-21-07-018; Check No. 688007; Refund of 10,000 paid under Voucher No. 300-2021-07-19; Check No. 688008 | 10000
Share of the City-2012 7171 Excise Tax- | [10 empty] | 0
Construction/Rehabilitation of Farm to Market Road | 22 rural barangays | 34500000 | October,2015 |  | 100% | 34167234.31 | 332765.69 | 34167234.31 |  | completed | 332765.69
Share of the City-Direct shares of Congressional Districts for the 2012 Excise Tax: | [10 empty] | 0
Farm to Market Road | rural barangays | 15000000 | November,2015 |  | 100% | 14280464.15 | 719535.85 | 14280464.15 |  | completed | 719535.85
Purchase of Various Equipment | 43 barangays | 40745187 | November,2015 |  | 92.15% | 37546995 | 12597192 | 37546995 |  | ongoing | 3198192
Buy -back and Other Marketing | [10 empty] | 0
Programs for Critical Alternative crops to tobacco |  | 4000000 | November,2015 |  | 89.55% | 3581998.24 | 418001.76 | 3581998.24 |  | ongoing | 418001.76
Local Government Support Fund: | [10 empty] | 0
SALINTUBIG(Sagana at Ligtas na Tubig sa Lahat) Provision of Portable Water Supply | [9 empty] | For Final Billing | 0
| Pimentel | 500000 | 2017-10-22 |  | 100% | [5 empty] | 500000
| Maipalig | 1060000 | 2017-10-22 |  | 100% | [5 empty] | 1060000
0
FY 2020 Local Government Support Fund-Assistance to Cities (Riverfront Promenade 3) |  | 10647492 | Receipt of Fund- November 2021 | [6 empty] | ongoing | 10647492
Local Government Support Fund- Financial Assistance to LGUs (Procurement of Rescue Kit) |  | 2500000 | Receipt of Fund -December 2022 | [7 empty] | 2500000
DSWD-RF01 | [10 empty] | 0
Cost for Viand and Rice for 1,050 Children in the implementation of SFP CY 2017 |  | 1890000 | Receipt of Fund-September 2018 |  | 50.21% | 948991.96 | 1890000 |  |  | Fully Liquidated, with a refund of 941,008.04; Check No. 638772 | 941008.04
Fund Transfer-Social Pension 3rd Qtr |  | 1264500 | Receipt of Fund-October 2018 |  | 100% | 1264500 | 0 | 1264500 |  | liquidated | 0
Fund Transfer-Social Pension 4th Qtr |  | 1264500 | Receipt of Fund-October 2018 |  | 100% | 1264500 | 0 | 1264500 |  | liquidated | 0
ATI-RTC I | [10 empty] | 0
Funding Support for the Sustainable Community Development Through the Conduct of Series of Training Under the Extension Program fro Agri-Fisheries and National Development (Expand) or Grant System |  | 905000 | Receipt of Fund-December 27, 2018 |  | 100% | 876294.28 | 28705.72 | 111357.38 |  | liquidated with refund of 28,705.71 Check # 638717 | 28705.72
DEPARTMENT OF ENERGY | [10 empty] | 0
ER 1-94 COVID related projects of the City Government of Batac (from the DOE) | City of Batac, Ilocos Norte | 200000 | August 2020 |  | 100% | 193836 |  |  |  | According to DOE, the balance of P6,164 will be used to purchase alcohol. | 6164
DANGEROUS DRUGS BOARD | [10 empty] | 0
Financial Assistance-Dangerous Drugs Board |  | 6000000 | Receipt of Fund- December 2021 | [6 empty] | Pre-Proc Conference on October 17, 2022 | 6000000
OFFICE OF THE PRESIDENT | [10 empty] | 0
Financial Assistance to cater and address the immediate needs of the people affected by the health crisis brought about by the Corona Virus Disease (COVID-19) per approved Memorandum dated March 4, 2021 | City of Batac, Ilocos Norte | 5000000 | Receipt of Fund March 2021 |  | 100% | 4963262 |  |  |  | Liquidated with refund to Office of the President amounting to P36,738.00 under Check No. 638811 | 36738
Financial assistance of people affected by Covid-19 | City of Batac, Ilocos Norte | 10000000 | July 2022 |  | 0% | 0 |  |  |  | Refunded to OP-Socio Civic Projects Fund under Check No. 638814
DEPARTMENT OF HEALTH-CENTER FOR HEALTH DEVT. I
One Covid-19 Allowance (OCA)- for the month of January 2022 |  | 732125 | Receipt of Fund- July 25, 2022 |  | 98.77% | 723125 |  |  |  | Liquidated; Balance of 9,000 refunded under Check No. 638818 dated August 17, 2022
One Covid-19 Allowance (OCA)- for the month of February 2022 |  | 799125 | Receipt of Fund- July 25, 2022 |  | 100% | 799125 |  |  |  | Liquidated
Meals, accomodation & transportation benegits as per Admin Order #2021-0062 for the period Sept 15 to Dec 19, 2020 |  | 210000 | Receipt of Fund- July 25, 2022 |  | 96.67% | 203000 |  |  |  | Liquidated. Balance of 7,000 refunded under Check No. 638818 dated August 17, 2022
One Covid Allowance for the month of April 2022 |  | 709625 |  |  | 75.16% | 533375 |  |  |  | One Covid Allowance for BHWs and some Job Orders in process. | 176250
One Covid Allowance for the month of June 2022 |  | 650625 |  |  | 82.48% | 536625 |  |  |  | One Covid Allowance for BHWs and some Job Orders in process. | 114000
Generics Awareness Month |  | 46600 | Receipt of Fund- October 2022 |  | 5.617% | 2617.4 |  |  |  |  | 43982.6
DSWD-RO I | [10 empty] | 0
Rehabilitation of Senior Citizen Building | [9 empty] | liquidating damages in the amount of P20,809.15 | 0
DEPARTMENT OF LABOR AND EMPLOYMENT RO1 | [10 empty] | 0
DOLE Regional Office 1 (Provision of various Processing Equpment for Peanut Processing (Self-Employed with insuficient income) |  | 758152 | Receipt of Fund- October 2022 |  | 0% | 0
Others: | [10 empty] | 0
C and G Environmental Management Corporation |  | 121000 | Receipt of Fund- September 2022
Commission on Population & Development (Social Protection for Adolescent Mothers and their Children) |  | 200000 | Receipt of Fund- September 2022 |  | 21% | 42000 |  |  |  |  | 158000
911 Library - The Delivery of Supplementary Reference and Research Materials through an Accessible Community Satellite Library for Modular Learning of the Learners of the Three Barangays (Bungon, Baay and Billoca) | Brgy. Bungon, Baay and Billoca | 270000 | Receipt of Fund-August 31, 2022 |  |  | 0 |  |  |  |  | 270000
PBSP-CHO PMDT |  | 7610 | December 2017 |  | 0% | 0 |  |  |  |  | 7610
Sustainable Development Goals-Family Based Actions for Children and their Environment in the Slims (SDG FACES) |  | 50000 | November 2017 |  | 0% | 0 |  |  |  | not implemented | 50000
Cash Donation Support to PNCR-Ilocos Norte Chapter |  | 3000 | March 2017 |  | 0% | 0 |  |  |  |  | 3000 | 9. Commission on Polpulation & Development (Social Protection for Adolescent Mothers and their Children)
Prizes for Most Outstanding Farmers |  | 100000 | January 2017 |  | 0% | 0 |  |  |  |  | 100000 | 8. C and G Environmental Management Corporation
Travelling Allowance for existing BNS for 2019 |  | 56400 | Receipt of Fund-June 2019 |  | 100% | 56400 |  |  |  | completed | 0
SOCIAL AMELIORATION PROGRAM | City of Batac, Ilocos Norte | 51700000 | April 2020 |  | 100% | 51700000 |  |  |  | Fully liquidated | 0
SOCIAL PENSION for Indigent Senior Citizen for the 1st Semester of 2020 | City of Batac, Ilocos Norte | 2319000 | June 2020 |  | 100% | 2319000 |  |  |  | Fully Liquidated, with a refund of 114,000; Check No. 638768 | 0
Provision of Water Pumps (Department of Labor and Employment) | City of Batac, Ilocos Norte | 1400000 | July 2020 |  | 100% | 1399950 |  |  |  | Voucher and check of refund in the amount of P50.00 was prepared under V#300-2021-03-009; check#638783 | 50
Travelling Allowance for existing BNS for 2022 |  | 55200 | Receipt of Fund-May 23, 2022 |  | 0% | 55200 |  |  |  |  | 0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
| FLORIDA S. CADANO |  |  |  |  | ENGR. ALBERT D. CHUA
| City Accountant |  |  |  |  | City Mayor

## UNLIQUIDATED CASH ADVANCES
FDP Form 12 - Unliquidated Cash Advances
UNLIQUIDATED CASH ADVANCES
As of DECEMBER 31, 2022
City of Batac, Ilocos Norte - General Fund
Name of Debtor | Amount |  |  |  | Amount Due
(In alphabetical order) | Balance |  | Date Granted | Purpose | Current |  |  | Past Due
[5 empty] | Less than 30 days | 31-90 days | 91-365 days | Over 1 year | Over 2 years | 3 years and above
NONE
TOTAL | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
We hereby certify that we have reveiwed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
FLORIDA S. CADANO | [5 empty] | ENGR. ALBERT D. CHUA
City Accountant | [5 empty] | City Mayor
0

## CASH FLOW 4TH QTR
FDP Form 9 - Statement of Cash Flow
(COA Form)
STATEMENT OF CASH FLOWS
For the Period Ended December 31, 2022
City of Batac, Ilocos Norte
ALL FUNDS
Cash Flows from Operating Activities:
Cash Inflows:
|  | Collection from Taxpayers |  | 64618702.39
|  | Share from Internal Revenue Collections |  | 741305374
|  | Other Share from National Taxes |  | 259283152.84
|  | Receipts from Sale of Goods or Services |  | 59155032.37
|  | Interest Income |  | 2535617.69
|  | Other Receipts |  | 95910067.18
|  | Total Cash Inflows |  | 1222807946.47
Cash Outflows:
Payments:
|  |  | Of Expenses | 326478583.63
|  |  | To Suppliers/Creditors | 164370360.41
|  |  | To Employees | 106311047.8
|  | Other Expenses |  | 159493214.91
|  | Total Cash Outflows |  | 756653206.75
| Net Cash from Operating Activities |  |  |  | 466154739.72
Cash Flows from Investing Activities
Cash Inflows:
|  | From Sale of Property, Plant and Equipment |  | 0
|  | From Sale of Dept Securities of Other Entities |  | 0
From Collection of Principal on Loans
|  |  | to Other Entities | 0
|  | Total Cash Inflows |  | 0
Cash Outflows:
|  | To Purchase Property, Plant & Equipment |  | 115867022.42
|  | To Purchase Debt Securities of Other Entities |  | 0
|  | To Grant/Make Loans to Other Entities |  | 0
|  | Total Cash Outflows |  | 115867022.42
| Net Cash from Investing Activities |  |  |  | -115867022.42
Cash Flows from Financing Activities
Cash Inflows:
|  | From Issuance of Debt Securities |  | 0
|  | From Acquisition of Loan |  | 0
|  | Total Cash Inflows |  | 0
Cash Outflows:
|  | Retirement/Redemption of Debt Securities |  | 0
|  | Payment of Loan Amortization |  | 0
|  | Total Cash Outflows |  | 0
| Net Cash from Financing Activities |  |  |  | 0
Net Increase in Cash |  |  |  |  | 350287717.3
Cash Beginning of the Period, January 1, 2022 |  |  |  |  | 1851886217
Cash at the End of the Period, December 31, 2022 |  |  |  |  | 2202173934.3
CERTIFIED CORRECT: |  |  |  | NOTED BY:
FLORIDA S. CADANO |  |  |  | ENGR. ALBERT D. CHUA
| City Accountant |  |  | City Mayor