## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | I | CALENDAR YEAR: | 2023 | [13 empty] | 2023
PROVINCE: | ILOCOS NORTE | QUARTER: | 2 | [13 empty] | SECOND
CITY/MUNICIPALITY: | BATAC
FUNCTION/PROGRAM PROJECT ACTIVITY |  |  | LOCATION/COVERAGE | TOTAL COST | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | NO. OF EXTENSIONS, IF ANY | REMARKS
[19 empty] | % OF COMPLETION | TOTAL COST INCURRED
SOCIAL DEVELOPMENT
| Support to COVID-19 related PPAs |  | All Barangays | 1157843.8 | [13 empty] | Jan.-Dec. 2023 | 0% | 0
| Sub-total |  |  | 1157843.8 | [15 empty] | 0
ECONOMIC DEVELOPMENT
| Purchase of Tail Lift (1 ton capacity) |  | Slaughterhouse | 150000 | [13 empty] | Jan.-Dec. 2023 | 0% | 0
| Purchase of Fertilizer for distribution to Farmers |  | Rural Barangays | 80000000 | [13 empty] | Jan.-Dec. 2023 | 79.19% | 63348825 |  | Procurement on going
| Purchase of Palay Seeds for Distribution to Farmers |  | Rural Barangays | 20000000 | [13 empty] | Jan.-Dec. 2023 | 25.63% | 5126000 |  | Procurement on going
| Purchase of Assorted Hybrid Vegetables Seeds for Distribution to Farmers |  | Rural Barangays | 2000000 | [13 empty] | Jan.-Dec. 2023 | 0% | 0 |  | Procurement on going
| Purchase & Installation of Public Address System for the whole public market with complete accessories |  | Public Market | 500000 | [13 empty] | Jan.-Dec. 2023 | 0% | 0
| Acquisition of 1 unit Digital Weighing Scale for Hogs and Large Animals |  | Slaughterhouse | 1000000 | [13 empty] | Jan.-Dec. 2023 | 0% | 0
| Purchase of Weighing Scale for Distribution to Barangay |  | All Barangays | 1000000 | [13 empty] | Jan.-Dec. 2023 | 0% | 0 |  | Procurement on going
| Sub-total |  |  | 104650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0482 | 68474825
ENVIRONMENTAL MANAGEMENT
Solid Waste management Implementation
| Purchase of 2 units Garbage Compactor |  |  | 5000000 | [13 empty] | Jan.-Dec. 2023 | 0% | 0 |  | Procurement on going
| Purchase of 2 units Dump Truck |  |  | 10000000 | [13 empty] | Jan.-Dec. 2023 | 0% | 0 |  | Procurement on going
| Purchase of 2 units Forward Truck (Drop-side) |  |  | 6000000 | [13 empty] | Jan.-Dec. 2023 | 0% | 0 |  | Procurement on going
| Sub-total |  |  | 21000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | 0
| TOTAL SPA-20% DF |  |  | 126807843.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 54% | 68474825
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
| WILMA T. ICUSPIT | ENGR. ALBERT D. CHUA
| City Budget Officer | City Mayor

## FORM 12
FDP Form 12 - Unliquidated Cash Advances
UNLIQUIDATED CASH ADVANCES
REGION: REGION I |  |  | CALENDAR YEAR: | 2023
PROVINCE: ILOCOS NORTE |  |  | QUARTER: | 2
CITY/MUNICIPALITY: CITY GOVERNMENT OF BATAC
Name of Debtor (in alphabetical order) | Amount Balance | Date Granted | Purpose | Amount Due
|  |  |  | Current |  |  | Past Due
|  |  |  | Less than 30 days | 31-90 days | 91-365 days | Over 1 year | Over 2 years | 3 years and above
Anne Bernadeth C. Samsam | 2650 | 2023-06-19 | Travel | 2650
Ariel R. Austria | 8250 | 2023-06-26 | Travel | 8250
Christopher B. Lagmay | 23400 | 2023-06-19 | Travel | 23400
Joselle Mariya C. Arcibal | 10800 | 2023-06-21 | Travel | 10800
Kathleen Joy C. Acosta | 1000 | 2023-06-15 | Travel | 1000
Kylie B. Diao | 16000 | 2023-06-20 | Registration Fee | 16000
Lucky Rene G. Bunye | 23400 | 2023-06-19 | Travel | 23400
Rose Marie A. Oallesma | 10800 | 2023-06-21 | Travel | 10800
Sherryl Mae V. Ulit | 10800 | 2023-06-21 | Travel | 10800
Vanny C. Gamet | 8000 | 2023-06-22 | Registration Fee | 8000
Total | 115100 |  |  | 115100
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
SGD
JOSELLE MARIYA C. ARCIBAL |  |  | ENGR. ALBERT D. CHUA
Acting City Accountant |  |  | Local Chief Executive

## FORM 13
FDP Form 13 - Manpower Complement
HUMAN RESOURCE COMPLEMENT
REGION: REGION I |  | CALENDAR YEAR: | 2023
PROVINCE: ILOCOS NORTE |  | QUARTER: | 2
CITY/MUNICIPALITY: CITY GOVERNMENT OF BATAC
Nature of Appointment or Employment | Number | Compensation and Other Benefits |  | Total
|  | Salaries and Wages | Other Monetary Benefits
I. Permanent | 251 | 40661262.56 | 23661973.68 | 64323236.24
II. Contractual
III. Job Order/Contract of Service | 196 | 12332239.79 |  | 12332239.79
IV. Casual | 71 | 4446888.49 | 3039836.55 | 7486725.04
Grand Total | 518 | 57440390.84 | 26701810.23 | 84142201.07 | 71809961.28
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
SGD
MARLON F. SORIA |  | JOSELLE MARIYA C. ARCIBAL |  | ENGR. ALBERT D. CHUA
Human Resource Management Officer |  | Acting City Accountant |  | Local Chief Executive
Notes:
1. Contractual personnel are those whose employment in the government is in accordance with a special contract to undertake a specific work or job, requiring special or technical skills not available in the employing agency, to be accomplished within a specific period, which in no case shall exceed one year, and performs or accomplishes the specific work or job, under his own responsibility with a minimum of direction and supervision from the hiring agency. (Source: Presidential Decress No. 807 October 6, 1975) 2.Contract of Services/Job Orders are employees whose services rendered are not considered government services and do not enjoy the benefits enjoyed by government employees. The job order covers piece work or intermittent job of short duration not exceeding six months on a daily basis. (Source: Omnibus Rules Implementing Book V of E.O. No. 292 and Other Pertinent Civil Service Laws)

## FORM 11
FDP Form 11 - SEF Utilization
(Deped-DBM-DILG Joint Circular No. 1 s. 2017, SEF Budget Accountability Form No. 1)
SPECIAL EDUCATION FUND
REGION: 1 |  | CALENDAR YEAR: 2023
PROVINCE: ILOCOS NORTE |  | QUARTER: 2
CITY/MUNICIPALITY: BATAC
[5 empty] | JANUARY | FEBRUARY | MARCH |  | APRIL |  | MAY |  | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER
City of Batac, Ilocos Norte
Receipt from SEF |  |  | P | 12775107.28
Less : | DISBURSEMENTS (broken down down by expense class and
by object of expenditures)
Personal Services
0
0
Maintenance and Other Operating Expenses
| Travelling Expenses | 5-01-01-010 |  | 767720 |  |  |  |  | 163850 |  | 63870 |  | 540000
[8 empty] | 04-001 | 70400 | 05-001 | 63870 | 05-003 | 540000
[8 empty] | 04-002 | 320
[8 empty] | 04-003 | 93130
| Training Expenses | 5-02-02-010 |  | 1727865 |  |  |  |  | 1222755 |  | 494805.45 |  | 10304.55
[8 empty] | 04-001 | 457700 | 05-001 | 474810 | 06-001 | 4769.75
[8 empty] | 04-002 | 7415 | 05-004 | 19995.45 | 06-002 | 5534.8
[8 empty] | 04-003 | 757640
| Insurance Expenses | 5-02-16-030 |  | 18120 | [6 empty] | 18120
[10 empty] | 05-003 | 18120
| Other Maintenance and Operating Expenses | 5-02-99-990 |  | 1456920 | [6 empty] | 1456920
[10 empty] | 05-002 | 1456920
Capital Outlays
0
Financial Expenses
0
|  | Sub-total |  | 3970625
|  | Balance | P | 8804482.28
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
JOSELLE MARIYA C. ARCIBAL |  | ENGR. ALBERT D. CHUA
Acting City Accountant |  | Local Chief Executive
Chairman, Local School Board

## FORM 8
FDP Form 8 - Local Disaster Risk Reduction and Management Fund Utilization
(Commission on Audit)
LOCAL DISASTER RISK REDUCTION AND MANAGEMENT FUND UTILIZATION
REGION: I |  |  | CALENDAR YEAR: 2023
PROVINCE: ILOCOS NORTE |  |  | QUARTER: 2 (APRIL)
CITY/MUNICIPALITY: BATAC
Particulars | Quick Response Fund (QRF) 30% | Mitigation Fund (70%) | NDRRMF | From Other LGUs | From Other Sources | Total
A. Sources of Funds:
Currrent Appropriation | 11311184.72 | 26392764.36 |  |  |  | 37703949.08
Continuing Appropriation | [5 empty] | 49222130.1
2022 |  | 13260620
2021 |  | 5400000
2020 |  | 7288525
2019 |  | 8553545
2018 |  | 2339826.94
2017 |  | 7614696.5
2016 |  | 4764916.66
Previous Year's Appropriations transferred to the Special Trust Fund | [5 empty] | 48494931.49
2019 |  | 11435457.97
2020 |  | 6683258.27
2021 |  | 8583365.77
2022 |  | 21792849.48
Donations |  | 3000 |  |  |  | 3000
Total Funds Available | 11311184.72 | 124112825.95 |  |  | 0 | 135424010.67
B. Utilization
Disaster Prevention and Mitigation
Clearing, pruning, brushing & cutting of trees in different barangays & schools |  | 71262.1 | [5 empty] | 10766 |  | 19908.7 |  | 40587.4
[7 empty] | 02-299 | 5508.7 | 03-040 | 8667.4 | 04-215 | 29436.1
[7 empty] | 02-300 | 5257.3 | 03-315 | 5424.4 | 04-374 | 5809.4
[9 empty] | 03-531 | 5816.9 | 04-375 | 5341.9
Cash for work program before calamities |  | 0
Dredging, declogging, & cleaning of rivers, creeks, canals, small farm reservoirs & other waterways |  | 0
Disaster Preparedness
Conduct of capacity training of C/BDRRMC, SDRRMC, NGOs, Govt & private sectors & volunteers on DRRM |  | 9500 | [7 empty] | 9500
[9 empty] | 03-316 | 9500
Updating of various CDRRM plans |  | 0
Conduct of earthquake, flood & fire evacuation drills Oplan Ligtas Pamayanan |  | 0
Info Education Campaign; Early Warning Systems & Pre-evacuation Management, Disaster preparedness; production, |  | 0
formulation & distribution of materials (manuals, leaflets, pamphlets, flyers, brochures, posters, early warning
signages); dialogues with the school & community; and others
Conduct of DRRM Related Contest |  | 68000 | [7 empty] | 68000
[9 empty] | 03-414 | 68000
Stockpiling & Prepositionig of Supplies & Materials (Food & Nonfood items/medicines) |  | 0
Acquisition of SRR eqpt. Personal protective gears & other facilities, materials, supplies and maintenance of evacuation center |  | 0
Purchase of 1 unit Laptop Computer |  | 0
Purchase of 1 unit Dekstop Computer |  | 0
Purchase of 1 set Multi-hazard Early Warning Device |  | 0
Purchase of 2 sets CPR Mannequin |  | 0
Purchase of 1 set Air-lifting Flat Bags |  | 0
Purchase of 1 set Vehicle Stabilization Kit |  | 0
Disaster Response, Rehabilitation and Recovery
Quick Response Fund | 0
Provision of basic needs of evacuees, responders & other staff on-duty (food, clothing, shelter, medicines & others) |  | 0
& other services
Cash for work program every after calamities |  | 0
Infrastructure rehabilitaion- rehab/repair/maintenance of calamity & disaster damages |  | 0
Gravelling of road shoulders & backfilling potholes |  | 0
Stockpiling of gravel and sand for regravelling of roadshoulders and backfilling potholes |  | 0
Agricultural rehabilitation program for Agriculture, Fishery & Livestock |  | 0
Emergency Shelter Assistance |  | 0
Total Utilization | 0 | 148762.1
Unutilized Balance | 11311184.72 | 123964063.85 |  |  |  | 135275248.57
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
SGD | SGD
ARVIN FRANCIS N. LUMANG | JOSELLE MARIYA C. ARCIBAL |  |  | ENGR. ALBERT D. CHUA
CDRRMO | Acting City Accountant |  |  | City Mayor

## Form 6a -TFU
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
REGION: | 1 |  | CALENDAR YEAR: | 2023
PROVINCE: | ILOCOS NORTE |  | QUARTER: | 2
CITY/MUNICIPALITY: | CITY OF BATAC
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Philhealth Capitation |  | 12906684.2 | 2011-2017 |  | 73.03% | 9426042.97 |  | ongoing
Animal Bite Treatment Package |  | 1130000 | February 2017 |  | 99.5% | 1124557 |  | ongoing
TB-DOTS |  | 399975 | 2015-2017 |  | 68.48% | 273901 |  | ongoing
HCI Charges |  | 574675 | 2018-2019 |  | 0%
Share of the City-2012 7171 Excise Tax-
Construction/Rehabilitation of Farm to Market Road | 22 rural barangays | 34500000 | October,2015 |  | 100% | 34167234.31 |  | completed
Share of the City-Direct shares of Congressional Districts for the 2012 Excise Tax:
Farm to Market Road | rural barangays | 15000000 | November,2015 |  | 100% | 14280464.15 |  | completed
Purchase of Various Equipment | 43 barangays | 40745187 | November,2015 |  | 92.15% | 37546995 |  | ongoing
Buy -back and Other Marketing
Programs for Critical Alternative crops to tobacco |  | 4000000 | November,2015 |  | 89.55% | 3581998.24 |  | ongoing
Local Government Support Fund:
SALINTUBIG(Sagana at Ligtas na Tubig sa Lahat) Provision of Portable Water Supply | [7 empty] | For Final Billing
| Pimentel | 500000 | 2017-10-22 |  | 100%
| Maipalig | 1060000 | 2017-10-22 |  | 100%
FY 2020 Local Government Support Fund-Assistance to Cities (Riverfront Promenade 3) |  | 10647492 | Receipt of Fund- November 2021 |  |  |  |  | Notice to Proceed already issued to the Contractor.
Local Government Support Fund- Financial Assistance to LGUs (Procurement of Rescue Kit) |  | 2500000 | Receipt of Fund -December 2022 |  |  |  |  | Notice to Proceed already issued to the Contractor.
DEPARTMENT OF ENERGY
ER 1-94 COVID related projects of the City Government of Batac (from the DOE) | City of Batac, Ilocos Norte | 200000 | August 2020 |  | 100% | 193836 |  | According to DOE, the balance of P6,164 will be used to purchase alcohol.
DANGEROUS DRUGS BOARD
Financial Assistance-Dangerous Drugs Board |  | 6000000 | Receipt of Fund- December 2021 |  | 50% | 0 |  | Project Ongoing
DEPARTMENT OF HEALTH-CENTER FOR HEALTH DEVT. I
Generics Awareness Month |  | 46600 | Receipt of Fund- October 2022 |  | 80.72% | 37617.4
DEPARTMENT OF LABOR AND EMPLOYMENT RO1
DOLE Regional Office 1 (Provision of various Processing Equpment for Peanut Processing (Self-Employed with insuficient income) |  | 758152 | Receipt of Fund- October 2022 |  | 0% | 0 |  | Notice to Proceed already issued to the Supplier
DEPARTMENT OF AGRICULTURE RFO1
Rehabilitation/Improvement of various small- scale irrigation projects (SSOPC) in City of Batac, Ilocos Norte |  | 26500000 | Receipt of Fund- March 2023 |  | 0%
Kadiwa Program |  | 5000000 | Receipt of Fund- April 2023 |  | 0%
Others:
C and G Environmental Management Corporation |  | 121000 | Receipt of Fund- September 2022 |  | 0%
Commission on Population & Development (Social Protection for Adolescent Mothers and their Children) |  | 200000 | Receipt of Fund- September 2022 |  | 52.5% | 105000
PBSP-CHO PMDT |  | 7610 | December 2017 |  | 0% | 0
Sustainable Development Goals-Family Based Actions for Children and their Environment in the Slims (SDG FACES) |  | 50000 | November 2017 |  | 0% | 0 |  | not implemented
Cash Donation Support to PNCR-Ilocos Norte Chapter |  | 3000 | March 2017 |  | 0% | 0
Prizes for Most Outstanding Farmers |  | 100000 | January 2017 |  | 0% | 0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
SGD
WILMA T. ICUSPIT |  |  | JOSELLE MARIYA C. ARCIBAL |  |  | ENGR. ALBERT D. CHUA
City Budget Officer |  |  | Acting City Accountant |  |  | City Mayor

## Form 2 - SIPB
Simplified Statement of Indebtedness, Payments and Balances (SIPB)
FDPP Form 2 - Annual Statement of Indebtedness, Payments and Balances
(DOF-BLGF Memorandum Circular No. 023-2019 dated September 19, 2019, Annex A)
Statement of Indebtedness, Payments and Balances (SIPB)
REGION: | REGION I - ILOCOS REGION | CALENDAR YEAR: | 2023
PROVINCE: | ILOCOS NORTE | QUARTER: | 2
CITY/MUNICIPALITY: | CITY OF BATAC
Instruction: Please prepare a Statement for each kind of loan.
ITEM NO. | PARTICULARS |  |  | DETAILS
1 | LGU Income Classification |  |  | fifth
2 | Date of Report |  |  | 2nd Quarter 2023
3 | Lending Institution (Bank or Creditor) |  |  | n/a
4 | Certificate Number - NDSC/BC |  |  | n/a
5 | Date of Certification - NDSC/BC |  |  | n/a
6 | Monetary Board (MB) Resolution Number
7 | Date of MB Opinion
8 | Date of Approval Loan
9 | Amount Approved*
10 | Maturity Date
11 | Type of Indebtedness Instrument (Loan, Bond or other form of indebtedness)
12 | Purpose of Indebtedness
13 | Terms and Conditions: Fixed or Variable
14 | Terms and Conditions: No. of Years of Indebtedness
15 | Terms and Conditions: Interest Rate
16 | Terms and Conditions: Grace Period (Number of Months or Years)
17 | Frequency of Payment
18 | Annual Amortization: Principal
19 | Annual Amortization: Interest
20 | Annual Amortization: Gross Receipt Tax (GRT)
21 | Starting Date of Payment
22 | Cumulative Payment from Starting Date: Principal
23 | Cumulative Payment from Starting Date: Interest
24 | Cumulative Payment from Starting Date: GRT
25 | Total Amount Released (Availment as of date)
26 | Remaining Balance to Date / Undrawn Amount (Line 9-25=26)
27 | Outstanding Loan Balance After Principal Payment (Line 9-22=27)
28 | Arrears: Principal (if any)
29 | Arrears: Interest (if any)
30 | Collateral Security
31 | Deposit to Bond Sinking Fund for the Year
32 | Sinking Fund Balance to Date, if any
33 | Breakdown of Fees and Other Related Costs (of loan)
34 | Other Relevant Terms and Conditions (of loan)
Certified Correct by: |  |  | Date Issued:
SGD
VANNY C. GAMET |  |  | 2023-04-28
Acting City Treasurer
Note:
*Please indicate if on a staggered basis.

## FORM 9
FDP Form 9 - Statement of Cash Flow
(BLGF Memorandum Circular No. 09 - 2012 dated February 21, 2012, Annex 2)
STATEMENT OF CASH FLOWS
ALL FUNDS
REGION: I |  |  |  | CALENDAR YEAR: 2023
PROVINCE: ILOCOS NORTE |  |  |  | QUARTER: 2
CITY/MUNICIPALITY: CITY OF BATAC
Cash Flows from Operating Activities:
| Cash Inflows: |  |  |  |  | JULY | AUG | SEPT | TOTAL
|  | Collection from Taxpayers |  | 144598343.5 |  | 3439015.48 | 147940480.48 | 699967.03 | 152079462.99
|  | Share from Internal Revenue Collections |  | 315442566 |  | 28338227 | 28338227 | 28338227 | 85014681
|  | Receipts from Sale of Goods or Services |  | 36863267.62 |  | 4047229.68 | 3381043.18 | 3296311.72 | 10724584.58
|  | Interest Income |  | 1275147.96 |  | 267487.57 | 266649.18 | 262327.28 | 796464.03
|  | Dividend Income |  | 0
|  | Other Receipts |  | 65652223.13 |  | 432257.56 | 4580703.73 | 587219.58 | 5600180.87
|  | Total Cash Inflows |  | 563831548.21 |  | 36524217.29 |  |  | 36524217.29
| Cash Outflows: | [7 empty] | 0
|  | Payments: |  |  |  | 2441617.41 | 4202385.27 | 2834830.73 | 9478833.41
|  |  | To Suppliers/Creditors | 198078969.62 |  | 93011.69 | 0 | 0 | 93011.69
|  |  | To Employees | 47598806.86 |  | 5653204.75 | 5833368.5 | 8052728.07 | 19539301.32
|  | Interest Income |  | 0
|  | Other Expenses |  | 85011338.14 |  | 4858458.61 | 9596221.49 | 8838815.92 | 23293496.02
|  | Total Cash Outflows |  | 330689114.62 |  | 13046292.46 |  |  | 13046292.46
| Net Cash from Operating Activities |  |  |  | 233142433.59 | 23477924.83 |  |  | 23477924.83
Cash Flows from Investing Activities | [8 empty] | 0
Cash Inflows:
|  | From Sale of Property, Plant and Equipment |  | 0
|  | From Sale of Debt Securities of Other Entities |  | 0
|  | From Collection of Principal on Loans | [6 empty] | 0
|  |  | to Other Entities | 0
|  | Total Cash Inflows |  | 0 |  | -7748.76 | 2992640.21 | 7527131.44 | 10512022.89
| Cash Outflows: |  |  |  |  | -7748.76 |  |  | -7748.76
|  | To Purchase Property, Plant & Equipment |  | 8731901.02 |  | 0 |  |  | 0
|  | To Purchase Debt Securities of Other Entities |  | 0
|  | To Grant/Make Loans to Other Entities |  | 0
|  | Total Cash Outflows |  | 8731901.02 |  |  |  |  | 0
| Net Cash from Investing Activities |  |  |  | -8731901.02 | 0 |  |  | 0
Cash Flows from Financing Activities
Cash Inflows:
|  | From Issuance of Debt Securities |  | 0
|  | From Acquisition of Loan |  | 0
|  | Total Cash Inflows |  | 0
Cash Outflows:
|  | Retirement/Redemption of Debt Securities |  | 0
|  | Payment of Loan Amortization |  | 0
|  | Total Cash Outflows |  | 0
| Net Cash from Financing Activities |  |  |  | 0
Net Increase in Cash |  |  |  |  | 224410532.57 | 627915908.91
Cash Beginning of the Period, January 1, 2023 |  |  |  |  | 2202173934.3 | 0
Cash at the End of the Period, June 30, 2023 |  |  |  |  | 2426584466.87
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
SGD
JOSELLE MARIYA C. ARCIBAL |  |  |  | ENGR. ALBERT D. CHUA
Accountant III, Acting City Accountant |  |  |  | City Mayor
224410532.57
-3.8743e-07

## FORM 11 SRE
BUREAU OF LOCAL GOVERNMENT FINANCE DEPARTMENT OF FINANCE http://blgf.gov.ph/
STATEMENT OF RECEIPTS AND EXPENDITURES
LGU: | BATAC CITY, ILOCOS NORTE
Period Covered: | Q4, 2022
Particulars |  | Income Target/ Budget Appropriation | General Fund | SEF | Total | % of General + SEF to Total Income (GF+SEF)
LOCAL SOURCES |  | 130,583,641.18 | 129,797,105.15 | 14,825,791.75 | 144,622,896.90 | 12.33 %
TAX REVENUE |  | 76,338,911.18 | 67,574,084.26 | 14,812,927.50 | 82,387,011.76 | 7.03 %
Real Property Tax |  | 31,148,116.60 | 19,452,473.20 | 14,812,927.50 | 34,265,400.70 | 2.92 %
Tax on Business |  | 42,860,000.00 | 45,193,757.45 | 0.00 | 45,193,757.45 | 3.85 %
Other Taxes |  | 2,330,794.58 | 2,927,853.61 | 0.00 | 2,927,853.61 | 0.25 %
NON-TAX REVENUE |  | 54,244,730.00 | 62,223,020.89 | 12,864.25 | 62,235,885.14 | 5.31 %
Regulatory Fees (Permits and Licenses) |  | 12,403,600.00 | 16,271,666.86 | 0.00 | 16,271,666.86 | 1.39 %
Service/User Charges (Service Income) |  | 8,212,000.00 | 11,760,512.23 | 0.00 | 11,760,512.23 | 1.00 %
Receipts from Economic Enterprises (Business Income) |  | 30,629,130.00 | 31,122,853.32 | 0.00 | 31,122,853.32 | 2.65 %
Other Receipts (Other General Income) |  | 3,000,000.00 | 3,067,988.48 | 12,864.25 | 3,080,852.73 | 0.26 %
EXTERNAL SOURCES |  | 741,305,374.00 | 1,027,975,698.03 | 0.00 | 1,027,975,698.03 | 87.67 %
Internal Revenue Allotment |  | 741,305,374.00 | 741,305,373.96 | 0.00 | 741,305,373.96 | 63.22 %
Other Shares from National Tax Collections |  | 0.00 | 259,576,717.55 | 0.00 | 259,576,717.55 | 22.14 %
Inter-Local Transfers |  | 0.00 | 106,990.00 | 0.00 | 106,990.00 | 0.01 %
Extraordinary Receipts/Grants/Donations/Aids |  | 0.00 | 26,986,616.52 | 0.00 | 26,986,616.52 | 2.30 %
TOTAL CURRENT OPERATING INCOME |  | 871,889,015.18 | 1,157,772,803.18 | 14,825,791.75 | 1,172,598,594.93 | 100.00 %
ADD: SUPPLEMENTAL BUDGET (UNAPPROPRIATED SURPLUS) FOR CURRENT OPERATING EXPENDITURES |  | 0.00 | 0.00 | 0.00 | 0.00
TOTAL AVAILABLE FOR CURRENT OPERATING EXPENDITURES |  | 871,889,015.18 | 1,157,772,803.18 | 14,825,791.75 | 1,172,598,594.93
LESS: CURRENT OPERATING EXPENDITURES (PS + MOOE + FE)
General Public Services |  | 0.00 | 169,052,845.86 | 0.00 | 169,052,845.86 | 40.83 %
Education, Culture & Sports/Manpower Development |  | 0.00 | 10,899,674.45 | 866,745.00 | 11,766,419.45 | 2.84 %
Health, Nutrition & Population Control |  | 0.00 | 85,593,797.47 | 0.00 | 85,593,797.47 | 20.67 %
Labor and Employment |  | 0.00 | 1,522,550.99 | 0.00 | 1,522,550.99 | 0.37 %
Housing and Community Development |  | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 %
Social Services and Social Welfare |  | 0.00 | 26,985,178.72 | 0.00 | 26,985,178.72 | 6.52 %
Economic Services |  | 0.00 | 119,161,412.99 | 0.00 | 119,161,412.99 | 28.78 %
Debt Service (FE) (Interest Expense & Other Charges) |  | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 %
TOTAL CURRENT OPERATING EXPENDITURES |  | 0.00 | 413,215,460.48 | 866,745.00 | 414,082,205.48 | 100.00 %
NET OPERATING INCOME/(LOSS) FROM CURRENT OPERATIONS |  | 871,889,015.18 | 744,557,342.70 | 13,959,046.75 | 758,516,389.45 | 0.00 %
ADD: NON-INCOME RECEIPTS
CAPITAL/INVESTMENT RECEIPTS |  | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 %
Proceeds from Sale of Assets |  | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 %
Proceeds from Sale of Debt Securities of Other Entities |  | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 %
Collection of Loans Receivables |  | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 %
RECEIPTS FROM LOANS AND BORROWINGS (Payable) |  | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 %
Acquisition of Loans |  | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 %
Issuance of Bonds |  | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 %
OTHER NON-INCOME RECEIPTS |  | 0.00 | 0.00 | 0.00 | 0.00
TOTAL NON-INCOME RECEIPTS |  | 0.00 | 0.00 | 0.00 | 0.00
ADD: SUPPLEMENTAL BUDGET FOR CAPITAL OUTLAY |  | 0.00 | 0.00 | 0.00 | 0.00
TOTAL AMOUNT AVAILABLE FOR CAPITAL EXPENDITURES |  | 0.00 | 0.00 | 0.00 | 0.00
LESS: NON-OPERATING EXPENDITURES
CAPITAL/INVESTMENT EXPENDITURES |  | 0.00 | 26,411,002.62 | 441,870.00 | 26,852,872.62 | 100.00 %
Purchase/Construct of Property Plant and Equipment (Assets/Capital Outlay) |  | 0.00 | 26,411,002.62 | 441,870.00 | 26,852,872.62 | 100.00 %
Purchase of Debt Securities of Other Entities (Investment Outlay) |  | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 %
Grant/Make Loan to Other Entities (Investment Outlay) |  | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 %
DEBT SERVICE (Principal Cost) |  | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 %
Payment of Loan Amortization |  | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 %
Retirement/Redemption of Bonds/Debt Securities |  | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 %
OTHER NON-OPERATING EXPENDITURES |  | 0.00 | 0.00 | 0.00 | 0.00
TOTAL NON-OPERATING EXPENDITURES |  | 0.00 | 26,411,002.62 | 441,870.00 | 26,852,872.62
NET INCREASE/(DECREASE) IN FUNDS |  | 871,889,015.18 | 718,146,340.08 | 13,517,176.75 | 731,663,516.83
ADD: CASH BALANCE, BEGINNING |  | 1,801,046,460.27 | 1,773,234,609.61 | 27,811,850.66 | 1,801,046,460.27
FUND/CASH AVAILABLE |  | 2,672,935,475.45 | 2,491,380,949.69 | 41,329,027.41 | 2,532,709,977.10
Less: Payment of Prior Year/s Accounts Payable |  | 201,233,343.88 | 191,634,797.58 | 9,598,546.30 | 201,233,343.88
CONTINUING APPROPRIATION |  | 1,071,324,849.14 | 188,932,267.02 | 1,831,500.00 | 190,763,767.02
ADD: ADVANCE PAYMENT FOR RPT |  | 0.00 | 11,608,073.06 | 8,278,261.14 | 19,886,334.20
FUND/CASH BALANCE, END |  | 1,400,377,282.43 | 2,122,421,958.15 | 38,177,242.25 | 2,160,599,200.40
|  |  | GF | SEF | TOTAL
FUND/CASH BALANCE, END |  |  | 2,122,421,958.15 | 38,177,242.25 | 2,160,599,200.40
Amount set aside to finance projects with appropriations
provided in the previous years (Continuing appropriations) |  |  | 1,434,308,121.81 | 16,686,204.15 | 1,450,994,325.96
Amount set aside for payment of Accounts Payable |  |  | 313,715,275.56 | 13,406,142.90 | 327,121,418.46
Amount set aside for Obligation not yet Due and Demandable |  |  | 0.00 | 0.00 | 0.00
Amount Available for appropriations/operations |  |  | 374,398,560.78 | 8,084,895.20 | 382,483,455.98
Total Assets (net of accumulated depreciation) |  | 3,339,851,055.66
SGD
|  |  | Certified correct: | VANNY C. GAMET
Acting City Treasurer
|  | Generated by GARCIA, VERONICa DIRIC on |  |  | 15/03/2023 1.51 PM

## 3RD BID - OUT
FDP Form 10a-Bid Results on Goods & Services
Republic of the Philippines
GOODS & SERVICES BID-OUT
CITY OF BATAC
Third Quarter 2023
July - September
No. | BID ID No. | Name of Project | Approved Budget for Contract (In Php) | Winning Bidder | Name of Supplier | Address of Bidder | Bid Amount (In Php) | Date of Bidding | Pre-Proc Conference | Pre-bid Conference
1 | 9842590 | PURCHASE OF FUEL FOR STOCKPILING OF GRAVEL AND SAND FOR REGRAVELING OF ROAD SHOULDERS AND BACKFILLING OF POTHOLES | 1499200 | TRI-P FUEL AND OIL DISTRIBUTOR | TRI-P FUEL AND OIL DISTRIBUTOR | City of Batac | 1489830 | July 03, 2023 | May 15, 2023 | June 21, 2023
3 | 9887784 | PURCHASE OF 1 UNIT PHOTOCOPIER AND 1 UNIT DOCUMENT SCANNER | 650000 | SONKKENS OFFICE EQUIPMENT TRADING | SONKKENS OFFICE EQUIPMENT TRADING | Lipa City, Batangas | 631120 | July 05, 2023 | - | -
4 | 9902369 | PURCHASE OF VACCINES FOR THE NATIONAL IMMUNIZATION PROGRAM “BATA-BATACQUEÑO, PROTEKTADO | 550000 | ABM- A BUILDER MARKETING | ABM- A BUILDER MARKETING | Laoag City | 548500 | July 12, 2023 | - | -
5 | 9906717 | PURCHASE OF AIR CONDITIONING UNIT | 350000 | DIAMZON & GOPEZ REFRIGERATION & AIRCON IND. CO. | DIAMZON & GOPEZ REFRIGERATION & AIRCON IND. CO. | San Fernando City, Pampanga | 348800 | July 12, 2023 | - | -
6 | 9902392 | PURCHASE OF VARIOUS LABORATORY SUPPLIES | 801870 | ABM- A BUILDER MARKETING | ABM- A BUILDER MARKETING | Laoag City | 799223 | July 12, 2023 | - | -
7 | 9906706 | PURCHASE OF VARIOUS MATERIALS FOR THE MAINTENANCE OF HEAVY EQUIPMENT | 462165 | JOHN-HENRY CAR CARE CENTER | JOHN-HENRY CAR CARE CENTER | Laoag City | 462165 | July 12, 2023 | - | -
8 | 9916130 | PURCHASE OF GROCERY ITEMS FOR THE FOOD PACK DISTRIBUTION TO PWDs | 699750 | NEW JAVIER TRADING CORPORATION | NEW JAVIER TRADING CORPORATION | Bantay Ilocos Sur | 698040 | July 14, 2023 | - | -
9 | 9930010 | PURCHASE OF FUEL FOR FARM MACHINERY SERVICE TO FARMERS | 999951 | TRI-P FUEL AND OIL DISTRIBUTOR | TRI-P FUEL AND OIL DISTRIBUTOR | City of Batac | 999951 | July 19, 2023 | - | -
10 | 9906748 | PURCHASE OF JANITORIAL, CLEANING AND OTHER SUPPLIES AND MATERIALS | 3402678 | ABM- A BUILDER MARKETING | ABM- A BUILDER MARKETING | Laoag City | 3397231 | July 24, 2023 | April 14, 2023 | July 12, 2023
11 | 9902405 | PURCHASE OF VARIOUS LABORATORY REAGENTS | 2754781 | BDSCIENTIA MEDICAL AND DIAGNOSTIC SUPPLIES | BDSCIENTIA MEDICAL AND DIAGNOSTIC SUPPLIES | Baguio City | 2750842 | July 24, 2023 | May 29, 2023 | July 12, 2023
12 | 9902384 | PURCHASE OF VITAMINS FOR MICRONUTRIENT SUPPLEMENTATION | 2499240 | ABM- A BUILDER MARKETING | ABM- A BUILDER MARKETING | Laoag City | 2497320 | July 24, 2023 | June 9, 2023 | July 12, 2023
13 | 9902410 | PURCHASE OF VARIOUS MEDICINES AND VACCINES FOR THE CITY HEALTH OFFICE | 5393030 | ABM- A BUILDER MARKETING | ABM- A BUILDER MARKETING | Laoag City | 5389962 | July 24, 2023 | June 9, 2023 | July 12, 2023
14 | 10088252 | PURCHASE OF VACCINES FOR ANTI-RABIES PREVENTION AND CONTROL FOR THE THIRD AND FOURTH QUARTER OF 2023 | 787310 | ABM- A BUILDER MARKETING | ABM- A BUILDER MARKETING | Laoag City | 785810 | 2023-09-13 | - | -
15 | 10062450 | PURCHASE OF PIGLETS, FEED, AND MEDICINES TO BE DISTRIBUTED TO AFFECTED HOG RAISERS DUE TO AFRICAN SWINE FEVER | 4004000 | STY BATAC-AGRO INDUSTRIAL TRADING | STY BATAC-AGRO INDUSTRIAL TRADING | City of Batac | 3993220 | 2023-09-13 | August 4, 2023 | August 30, 2023
16 | 10100013 | PURCHASE OF PRINTERS FOR USE OF VARIOUS OFFICES, PUBLIC ELEMENTARY AND HIGH SCHOOLS | 999000 | MSTRIT.COM COMPUTER MARKETING AND SERVICES | MSTRIT.COM COMPUTER MARKETING AND SERVICES | Laoag City | 995695 | 2023-09-15 | - | -
17 | 10100212 | PURCHASE OF LAPTOP COMPUTERS FOR USE OF VARIOUS OFFICES | 711200 | MSTRIT.COM COMPUTER MARKETING AND SERVICES | MSTRIT.COM COMPUTER MARKETING AND SERVICES | Laoag City | 708720 | 2023-09-15 | - | -
18 | 10100062 | PURCHASE OF DESKTOP COMPUTERS FOR USE OF VARIOUS OFFICES | 535000 | MSTRIT.COM COMPUTER MARKETING AND SERVICES | MSTRIT.COM COMPUTER MARKETING AND SERVICES | Laoag City | 531990 | 2023-09-15 | - | -
19 | 10100279 | PURCHASE OF OFFICE EQUIPMENT (SMART TV AND SOUND SYSTEM) FOR SCHOOLS | 2177953.5 | MAXCORE TECHNOLGIES, INC. | MAXCORE TECHNOLGIES, INC. | Makati City, Metro Manila | 2174498 | 2023-09-27 |  | 2023-09-15
20 | 10100234 | PURCHASE OF LAPTOP COMPUTERS AND PRINTER FOR USE OF DIFFERENT SCHOOLS OF THE CITY OF BATAC | 2765000 | IEQUITY TECHNOLOGIES CORPORATION | IEQUITY TECHNOLOGIES CORPORATION | Ortigas CTR., San Antonio, Pasig City | 2759000 | 2023-09-27 |  | 2023-09-15
21 | 10152637 | PURCHASE OF VARIOUS LABORATORY SUPPLIES | 672532.75 | ABM- A BUILDER MARKETING | ABM- A BUILDER MARKETING | Laoag City | 671932.75 | 2023-09-29 | - | -
22 | 10152629 | PURCHASE OF VARIOUS LABORATORY REAGENTS | 990911 | BDSCIENTIA MEDICAL AND DIAGNOSTIC SUPPLIES | BDSCIENTIA MEDICAL AND DIAGNOSTIC SUPPLIES | Baguio City | 990000 | 2023-09-29 | - | -
x-x-x-x-x-x-x-x-x
We certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
MARLON F. SORIA WILMA T. ICUSPIT NORALYN I. MANAHAN HILARION G. NALUPTA NORIEL BENSON R. TABUNAN
BAC CHAIRMAN BAC VICE CHAIRMAN BAC MEMBER BAC MEMBER BAC MEMBER

## FORM 10 A
FDP Form 10a-Bid Results on Goods & Services
Republic of the Philippines
GOODS & SERVICES BID-OUT
CITY OF BATAC
Second Quarter 2023
JULY-SEPTEMBER
No. | BID ID No. | Name of Project | Approved Budget for Contract (In Php) | Winning Bidder | Name of Supplier | Address of Bidder | Bid Amount (In Php) | Date of Bidding | Pre-Proc Conference | Pre-bid Conference
1 | 9842590 | PURCHASE OF FUEL FOR STOCKPILING OF GRAVEL AND SAND FOR REGRAVELING OF ROAD SHOULDERS AND BACKFILLING OF POTHOLES | 1499200 | TRI-P FUEL AND OIL DISTRIBUTOR | TRI-P FUEL AND OIL DISTRIBUTOR | City of Batac | 1489830 | July 03, 2023 | May 15, 2023 | June 21, 2023
3 | 9887784 | PURCHASE OF 1 UNIT PHOTOCOPIER AND 1 UNIT DOCUMENT SCANNER | 650000 | SONKKENS OFFICE EQUIPMENT TRADING | SONKKENS OFFICE EQUIPMENT TRADING | Lipa City, Batangas | 631120 | July 05, 2023 | - | -
4 | 9902369 | PURCHASE OF VACCINES FOR THE NATIONAL IMMUNIZATION PROGRAM “BATA-BATACQUEÑO, PROTEKTADO | 550000 | ABM- A BUILDER MARKETING | ABM- A BUILDER MARKETING | Laoag City | 548500 | July 12, 2023 | - | -
5 | 9906717 | PURCHASE OF AIR CONDITIONING UNIT | 350000 | DIAMZON & GOPEZ REFRIGERATION & AIRCON IND. CO. | DIAMZON & GOPEZ REFRIGERATION & AIRCON IND. CO. | San Fernando City, Pampanga | 348800 | July 12, 2023 | - | -
6 | 9902392 | PURCHASE OF VARIOUS LABORATORY SUPPLIES | 801870 | ABM- A BUILDER MARKETING | ABM- A BUILDER MARKETING | Laoag City | 799223 | July 12, 2023 | - | -
7 | 9906706 | PURCHASE OF VARIOUS MATERIALS FOR THE MAINTENANCE OF HEAVY EQUIPMENT | 462165 | JOHN-HENRY CAR CARE CENTER | JOHN-HENRY CAR CARE CENTER | Laoag City | 462165 | July 12, 2023 | - | -
8 | 9916130 | PURCHASE OF GROCERY ITEMS FOR THE FOOD PACK DISTRIBUTION TO PWDs | 699750 | NEW JAVIER TRADING CORPORATION | NEW JAVIER TRADING CORPORATION | Bantay Ilocos Sur | 698040 | July 14, 2023 | - | -
9 | 9930010 | PURCHASE OF FUEL FOR FARM MACHINERY SERVICE TO FARMERS | 999951 | TRI-P FUEL AND OIL DISTRIBUTOR | TRI-P FUEL AND OIL DISTRIBUTOR | City of Batac | 999951 | July 19, 2023 | - | -
10 | 9906748 | PURCHASE OF JANITORIAL, CLEANING AND OTHER SUPPLIES AND MATERIALS | 3402678 | ABM- A BUILDER MARKETING | ABM- A BUILDER MARKETING | Laoag City | 3397231 | July 24, 2023 | April 14, 2023 | July 12, 2023
11 | 9902405 | PURCHASE OF VARIOUS LABORATORY REAGENTS | 2754781 | BDSCIENTIA MEDICAL AND DIAGNOSTIC SUPPLIES | BDSCIENTIA MEDICAL AND DIAGNOSTIC SUPPLIES | Baguio City | 2750842 | July 24, 2023 | May 29, 2023 | July 12, 2023
12 | 9902384 | PURCHASE OF VITAMINS FOR MICRONUTRIENT SUPPLEMENTATION | 2499240 | ABM- A BUILDER MARKETING | ABM- A BUILDER MARKETING | Laoag City | 2497320 | July 24, 2023 | June 9, 2023 | July 12, 2023
13 | 9902410 | PURCHASE OF VARIOUS MEDICINES AND VACCINES FOR THE CITY HEALTH OFFICE | 5393030 | ABM- A BUILDER MARKETING | ABM- A BUILDER MARKETING | Laoag City | 5389962 | July 24, 2023 | June 9, 2023 | July 12, 2023
14 | 10088252 | PURCHASE OF VACCINES FOR ANTI-RABIES PREVENTION AND CONTROL FOR THE THIRD AND FOURTH QUARTER OF 2023 | 787310 | ABM- A BUILDER MARKETING | ABM- A BUILDER MARKETING | Laoag City | 785810 | 2023-09-13 | - | -
15 | 10062450 | PURCHASE OF PIGLETS, FEED, AND MEDICINES TO BE DISTRIBUTED TO AFFECTED HOG RAISERS DUE TO AFRICAN SWINE FEVER | 4004000 | STY BATAC-AGRO INDUSTRIAL TRADING | STY BATAC-AGRO INDUSTRIAL TRADING | City of Batac | 3993220 | 2023-09-13 | August 4, 2023 | August 30, 2023
16 | 10100013 | PURCHASE OF PRINTERS FOR USE OF VARIOUS OFFICES, PUBLIC ELEMENTARY AND HIGH SCHOOLS | 999000 | MSTRIT.COM COMPUTER MARKETING AND SERVICES | MSTRIT.COM COMPUTER MARKETING AND SERVICES | Laoag City | 995695 | 2023-09-15 | - | -
17 | 10100212 | PURCHASE OF LAPTOP COMPUTERS FOR USE OF VARIOUS OFFICES | 711200 | MSTRIT.COM COMPUTER MARKETING AND SERVICES | MSTRIT.COM COMPUTER MARKETING AND SERVICES | Laoag City | 708720 | 2023-09-15 | - | -
18 | 10100062 | PURCHASE OF DESKTOP COMPUTERS FOR USE OF VARIOUS OFFICES | 535000 | MSTRIT.COM COMPUTER MARKETING AND SERVICES | MSTRIT.COM COMPUTER MARKETING AND SERVICES | Laoag City | 531990 | 2023-09-15 | - | -
19 | 10100279 | PURCHASE OF OFFICE EQUIPMENT (SMART TV AND SOUND SYSTEM) FOR SCHOOLS | 2177953.5 | MAXCORE TECHNOLGIES, INC. | MAXCORE TECHNOLGIES, INC. | Makati City, Metro Manila | 2174498 | 2023-09-27 |  | 2023-09-15
20 | 10100234 | PURCHASE OF LAPTOP COMPUTERS AND PRINTER FOR USE OF DIFFERENT SCHOOLS OF THE CITY OF BATAC | 2765000 | IEQUITY TECHNOLOGIES CORPORATION | IEQUITY TECHNOLOGIES CORPORATION | Ortigas CTR., San Antonio, Pasig City | 2759000 | 2023-09-27 |  | 2023-09-15
21 | 10152637 | PURCHASE OF VARIOUS LABORATORY SUPPLIES | 672532.75 | ABM- A BUILDER MARKETING | ABM- A BUILDER MARKETING | Laoag City | 671932.75 | 2023-09-29 | - | -
22 | 10152629 | PURCHASE OF VARIOUS LABORATORY REAGENTS | 990911 | BDSCIENTIA MEDICAL AND DIAGNOSTIC SUPPLIES | BDSCIENTIA MEDICAL AND DIAGNOSTIC SUPPLIES | Baguio City | 990000 | 2023-09-29 | - | -
x-x-x-x-x-x-x-x-x
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
SGD
| MICHELL G. MANUEL, CE. |  |  |  | MARLON F. SORIA
| BAC Secretariat Head |  |  |  | BAC Chairperson

## FORM 10 B
FDP Form 10a-Bid Results on Civil Works
Republic of the Philippines
CIVIL WORKS BID-OUT
BATAC CITY
Second Quarter 2023
JULY-SEPPTEMBER
No. | BID ID No. | Name of Project | Approved Budget for Contract (In Php) | Location | Winning Bidder | Name & Address | Bid Amount (In Php) | Bidding Date | Contract Duration (In Calendar Days base on pow) | Contract End Date | NOTICE OF AWARD DATE | DATE OF PRE-PROC
NONE
x-x-x-x-x-x-x-x-x-x-x-x-x-x-x-x
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
SGD
| MARK ANGELO V. SABAS |  |  |  | MARLON F. SORIA
| BAC Secretariat Head |  |  |  | BAC Chairperson

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2
43