## Form 6a -TFU
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
REGION: | 1 |  | CALENDAR YEAR: | 2023
PROVINCE: | ILOCOS NORTE |  | QUARTER: | 4
CITY/MUNICIPALITY: | CITY OF BATAC
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Philhealth Capitation |  | 12906684.2 | 2011-2017 |  | 73.03% | 9426042.97 |  | ongoing
Animal Bite Treatment Package |  | 1130000 | February 2017 |  | 99.5% | 1124557 |  | ongoing
TB-DOTS |  | 399975 | 2015-2017 |  | 68.48% | 273901 |  | ongoing
HCI Charges |  | 574675 | 2018-2019 |  | 0%
Riverfront Promenade Phase 2 | Brgy. Ablan & Valdez | 13750201 | Receipt of Fund-December 2019 |  | 90% | 4572740.74
Share of the City-2012 7171 Excise Tax-
Construction/Rehabilitation of Farm to Market Road | 22 rural barangays | 34500000 | October,2015 |  | 100% | 34167234.31 |  | completed
Share of the City-Direct shares of Congressional Districts for the 2012 Excise Tax:
Farm to Market Road | rural barangays | 15000000 | November,2015 |  | 100% | 14280464.15 |  | completed
Purchase of Various Equipment | 43 barangays | 40745187 | November,2015 |  | 92.15% | 37546995 |  | ongoing
Buy -back and Other Marketing
Programs for Critical Alternative crops to tobacco |  | 4000000 | November,2015 |  | 89.55% | 3581998.24 |  | ongoing
Local Government Support Fund:
SALINTUBIG(Sagana at Ligtas na Tubig sa Lahat) Provision of Portable Water Supply | [7 empty] | For Final Billing
| Pimentel | 500000 | 2017-10-22 |  | 100%
| Maipalig | 1060000 | 2017-10-22 |  | 100%
FY 2020 Local Government Support Fund-Assistance to Cities (Riverfront Promenade 3) |  | 10647492 | Receipt of Fund- November 2021 |  | 0% |  |  | Project not yet started.
Local Government Support Fund- Financial Assistance to LGUs (Procurement of Rescue Kit) |  | 2500000 | Receipt of Fund -December 2022 |  | 100% | 2480000 |  | Liquidated; balance of P20,000.00 already refunded to the Bureau of Treasury.
DEPARTMENT OF ENERGY
ER 1-94 COVID related projects of the City Government of Batac (from the DOE) | City of Batac, Ilocos Norte | 200000 | August 2020 |  | 100% | 193836 |  | According to DOE, the balance of P6,164 will be used to purchase alcohol.
DANGEROUS DRUGS BOARD
Financial Assistance-Dangerous Drugs Board |  | 6000000 | Receipt of Fund- December 2021 |  | 90% | 0 |  | Project Ongoing
DEPARTMENT OF HEALTH-CENTER FOR HEALTH DEVT. I
Generics Awareness Month |  | 46600 | Receipt of Fund- October 2022 |  | 80.72% | 37617.4 |  | Liquidated; DV for refund amounting to P8,982.60 already prepared but not yet received by DOH-CHD I
Health Emergency Allowance (HEA) for the months of July and August 2021. |  | 1963718.75 | Receipt of Fund- November 2023 |  | 100% | 1963718.75 |  | Liquidated
DEPARTMENT OF LABOR AND EMPLOYMENT RO1
DOLE Regional Office 1 (Provision of various Processing Equpment for Peanut Processing (Self-Employed with insuficient income) |  | 758152 | Receipt of Fund- October 2022 |  | 100% | 749410 |  | Liquidated; Balance of P8,742.00 already refunded to DOLE RO I
DEPARTMENT OF AGRICULTURE RFO1
Rehabilitation/Improvement of various small- scale irrigation projects (SSOPC) in City of Batac, Ilocos Norte |  | 26500000 | Receipt of Fund- March 2023 |  | 0%
Kadiwa Program |  | 5000000 | Receipt of Fund- April 2023 |  | 0%
Others:
C and G Environmental Management Corporation |  | 121000 | Receipt of Fund- September 2022 |  | 0%
Commission on Population & Development (Social Protection for Adolescent Mothers and their Children) |  | 200000 | Receipt of Fund- September 2022 |  | 52.5% | 105000 |  | Liquidated; DV for refund amounting to P95,0000 already prepared but not yet received by Commission on Population & Development
PBSP-CHO PMDT |  | 7610 | December 2017 |  | 0% | 0
Sustainable Development Goals-Family Based Actions for Children and their Environment in the Slims (SDG FACES) |  | 50000 | November 2017 |  | 0% | 0 |  | not implemented
Cash Donation Support to PNCR-Ilocos Norte Chapter |  | 3000 | March 2017 |  | 0% | 0
Prizes for Most Outstanding Farmers |  | 100000 | January 2017 |  | 0% | 0
Travelling Allowance for BNS |  | 55200 | July 2023 |  | 100% | 55200 |  | Liquidated; Already received by the BNS.
Fire Code Fees- 20% Share of LGUs (2018, 2020 & 2021) |  | 1190489.35 | August 2023 |  | 0%
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
WILMA T. ICUSPIT |  |  | JOSELLE MARIYA C. ARCIBAL |  |  | ENGR. ALBERT D. CHUA
City Budget Officer |  |  | Acting City Accountant |  |  | City Mayor

## Form 6b - TFU (hidden)
LOCAL GOVERNMENT SUPPORT FUND (Report on Fund Utilization and Status of Program/Project Implementation)
REGION: |  |  | CALENDAR YEAR:
PROVINCE: |  |  | QUARTER:
CITY/MUNICIPALITY: |  |  | OFFICE:
Amount
Fund Source | Date of Notice of Authority to Debit Account Issued | Type of Program/Project | Name Title of Program/Project | Specific Location | Mechanism/Mode of Implementation | Estimated Number of Beneficiaries | Received | Obligation | Disbursement | Estimated Completion (Month and Year) | Remarks on Program/Project Status
Certified Correct by: |  |  |  |  | Attested by:
The Local Finance Committee:
Local Chief Executive
City Budget Officer
City Treasurer
City Planning and Development Coordinator
Instructions:
1 | The report shall prepared by the LFC, in coordination with the other local officials concerned (local accountant on the allotment, obligation and disbursements;
local engineers in the status of infrastructure projects, as may be applicable.
2 | The fund source shall be based on the NADAI issued to the cities.
3 | The type of program/project shall be identified, consistent with the projects that may be implemented under the Circular.
4 | Amount received refers to the amount received by the city as its location. It is the amount the NADAI. Obligation refers to the total amount obligated by the
city as of reporting period. Disbursement refers to the total amount paid as of reporting period.
5 | The status of programs/projects refers to the percentage of physical completion or delivery of service as of reporting period.

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2
38