## 1st qtr
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 2nd QUARTER CY 2024
FUNCTION/PROGRAM PROJECT ACTIVITY |  |  | LOCATION/COVERAGE | TOTAL COST | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | NO. OF EXTENSIONS, IF ANY | REMARKS
[19 empty] | % OF COMPLETION | TOTAL COST INCURRED
SOCIAL DEVELOPMENT
| Provision of Food Assistance and Other Relief Goods for Affected Families during calamities |  | All Barangays | 12000000 | [13 empty] | Jan.-Dec. 2024 | 0%
| Provision of Medical Supplies and Medicines for re-emerging and emerging Infectious diseases |  | All Barangays | 1505181 | [13 empty] | Jan.-Dec. 2024
| Implementation of Community Based Monitoring System Integrating Household-Level Data Management System |  | All Barangays | 8500000 | [13 empty] | Jan.-Dec. 2024 | 0%
| Sub-total |  |  | 22005181 | [15 empty] | 0
ECONOMIC DEVELOPMENT
| Recovery Assistance to Farmers and Fisherfolks affected by typhoon and other calamities |  | All Barangays | 3000000 | [13 empty] | Jan.-Dec. 2024 | 0%
| Fuel Subsidy Program |  | All Barangays | 8000000 | [13 empty] | Jan.-Dec. 2024 | 0%
| Purchase of 1 unit Water Tanker |  | Public Market | 2000000 | [13 empty] | Jan.-Dec. 2024 | 0%
| Purchase of 1 unit Drop Side Truck (10 ft.) |  | Slaughterhouse | 2000000 | [13 empty] | Jan.-Dec. 2024 | 0% |  |  | Pipeline
| Purchase of 1 unit Reefer Van (14 ft.) |  | Slaughterhouse | 3000000 | [13 empty] | Jan.-Dec. 2024 | 0% |  |  | Pipeline
| Purchase of Fertilizer for Distribution to Farmers |  | All Farmers | 65000000 | [13 empty] | Jan.-Dec. 2024 | 97.72% | 63516287 |  | Procured
| Purchase of Palay Seeds for Distribution to Farmers |  | All Farmers | 7000000 | [13 empty] | Jan.-Dec. 2024 | 0% |  |  | Awarded
| Purchase of 1 unit Hauling Truck |  | Agriculture | 3000000 | [13 empty] | Jan.-Dec. 2024 | 0%
| Purchase of Assorted Hybrid Vegetables Seeds for Distribtution to Farmers |  | All Farmers | 2000000 | [13 empty] | Jan.-Dec. 2024 | 0% |  |  | For Award Notice Abstract
| Animal Dispersal Program |  | All Barangays | 5000000 | [13 empty] | Jan.-Dec. 2024 | 0%
| Sub-total |  |  | 100000000 | [15 empty] | 63516287
ENVIRONMENTAL MANAGEMENT
Solid Waste management Implementation
| Purchase of 1 unit Landfill Compactor |  |  | 8000000 | [13 empty] | Jan.-Dec. 2024 | 0%
| Purchase of 1 unit Garbage Truck |  |  | 4000000 | [13 empty] | Jan.-Dec. 2024 | 0%
| Sub-total |  |  | 12000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | 0
| TOTAL SPA-20% DF |  |  | 134005181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 47.4% | 63516287
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
|  | WILMA T. ICUSPIT | [16 empty] | ENGR. ALBERT D. CHUA
|  | City Budget Officer | [16 empty] | City Mayor

## 3rd
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 3rd QUARTER CY 2024
FUNCTION/PROGRAM PROJECT ACTIVITY |  |  | LOCATION/COVERAGE | TOTAL COST | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | NO. OF EXTENSIONS, IF ANY | REMARKS
[19 empty] | % OF COMPLETION | TOTAL COST INCURRED
SOCIAL DEVELOPMENT
| Provision of Food Assistance and Other Relief Goods for Affected Families during calamities |  | All Barangays | 12000000 | [13 empty] | Jan.-Dec. 2024 | 0%
| Provision of Medical Supplies and Medicines for re-emerging and emerging Infectious diseases |  | All Barangays | 1505181 | [13 empty] | Jan.-Dec. 2024
| Implementation of Community Based Monitoring System Integrating Household-Level Data Management System |  | All Barangays | 8500000 | [13 empty] | Jan.-Dec. 2024 | 0%
| Sub-total |  |  | 22005181 | [15 empty] | 0
ECONOMIC DEVELOPMENT
| Recovery Assistance to Farmers and Fisherfolks affected by typhoon and other calamities |  | All Barangays | 3000000 | [13 empty] | Jan.-Dec. 2024 | 0%
| Fuel Subsidy Program |  | All Barangays | 8000000 | [13 empty] | Jan.-Dec. 2024 | 0%
| Purchase of 1 unit Water Tanker |  | Public Market | 2000000 | [13 empty] | Jan.-Dec. 2024 | 0%
| Purchase of 1 unit Drop Side Truck (10 ft.) |  | Slaughterhouse | 2000000 | [13 empty] | Jan.-Dec. 2024 | 0% |  |  | Pipeline
| Purchase of 1 unit Reefer Van (14 ft.) |  | Slaughterhouse | 3000000 | [13 empty] | Jan.-Dec. 2024 | 0% |  |  | Pipeline
| Purchase of Fertilizer for Distribution to Farmers |  | All Farmers | 65000000 | [13 empty] | Jan.-Dec. 2024 | 0% |  |  | Procured
| Purchase of Palay Seeds for Distribution to Farmers |  | All Farmers | 7000000 | [13 empty] | Jan.-Dec. 2024 | 83.71% | 5860000 |  | procured
| Purchase of 1 unit Hauling Truck |  | Agriculture | 3000000 | [13 empty] | Jan.-Dec. 2024 | 0%
| Purchase of Assorted Hybrid Vegetables Seeds for Distribtution to Farmers |  | All Farmers | 2000000 | [13 empty] | Jan.-Dec. 2024 | 85.06% | 1701100 |  | procured
| Animal Dispersal Program |  | All Barangays | 5000000 | [13 empty] | Jan.-Dec. 2024 | 0%
| Sub-total |  |  | 100000000 | [15 empty] | 7561100
ENVIRONMENTAL MANAGEMENT
Solid Waste management Implementation
| Purchase of 1 unit Landfill Compactor |  |  | 8000000 | [13 empty] | Jan.-Dec. 2024 | 0%
| Purchase of 1 unit Garbage Truck |  |  | 4000000 | [13 empty] | Jan.-Dec. 2024 | 0%
| Sub-total |  |  | 12000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | 0
| TOTAL SPA-20% DF |  |  | 134005181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 5.642% | 7561100
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
|  | WILMA T. ICUSPIT | [16 empty] | ENGR. ALBERT D. CHUA
|  | City Budget Officer | [16 empty] | City Mayor